## Sheet1
|  | Multipurpose Arena | 2026-07-28 |  |  | Contract Log
|  | CURRENT CHANGE ORDER STATUS | [7 empty] | PAYMENTS |  | Off Project Payments by Work Order Number | [8 empty] | HECO-8
Contract | CO # | Description | Cost | Contract Amt. | Project | Off Project | Status | No. | Date | Total | Proj. Funds | 208818 | 249331 | 359873 | 393323 | 410308 | 438913 | 438917 | 446863 | Total | Budget | Contingency
[12 empty] | Dell | Boiler Plant | Electronics | Food Serv. | West Space | SMG Fac | SMG FF&E | Emer. ITC
BMC - 01 |  | Phase I | PO# 163401 | 608767 | [16 empty] | 608767 | 0
| 1 | Structural Peer review | 47000 |  | 47000 |  | comp | 1 | 2002-05-28 | 25000 | 25000
| 2 | MEP Peer Review | 27800 |  | 27800 |  | comp | 2 | 2002-08-06 | 100000 | 100000
| 3 | General conditions | 10461.66 |  | 10461.66 |  | comp | 3 | 2002-10-18 | 115000 | 115000
[5 empty] | 0 |  |  | 4 | 2002-11-19 | 70000 | 70000
[5 empty] | 0 |  |  | 5 | 2002-11-25 | 55000 | 55000
[5 empty] | 0 |  |  | 6 | 2003-01-08 | 90000 | 90000
[5 empty] | 0 |  |  | 7 | 2003-01-15 | 145000 | 145000
[5 empty] | 0 |  |  | 8 | 2003-02-20 | 65000 | 65000
[5 empty] | 0 |  |  | 9 | 2003-06-03 | 15000 | 15000
[5 empty] | 0 |  |  | 10 | 2003-07-16 | 14028.66 | 14028.66
Total |  |  | 85261.66 | 694028.66 | 694028.66 |  | 14.01% |  |  | 694028.66 | 694028.66
Balance | [9 empty] | 0 | [10 empty] | -85261.66
BMC - 01 |  | Phase II | P0# 253722 | 362158 | [16 empty] | 362158 | 0
| 1 | General conditions | 16164.58 |  | 16164.58 |  | comp | 1 | 2003-03-20 | 60000 | 60000
[5 empty] | 0 |  |  | 2 | 2003-04-09 | 100000 | 100000
[5 empty] | 0 |  |  | 3 | 2003-05-21 | 102000 | 102000
[5 empty] | 0 |  |  | 4 | 2003-06-03 | 100158 | 100158
[5 empty] | 0 |  |  | 5 | 2003-07-16 | 16164.58 | 16164.58
Total |  |  | 16164.58 | 378322.58 | 378322.58 |  | 4.463% |  |  | 378322.58 | 378322.58
Balance | [9 empty] | 0 | [10 empty] | -16164.58
BMC - 01 |  | Phase III | PO#284782 | 6823226.44 | [16 empty] | 8123226.44 | 1300000
| 1 | Final Struct. Peer Review | 5000 | 6828226.44 | 5000 |  | comp | 1 | 2003-08-01 | 262929.24 | 262929.24 | [8 empty] | 0
| 2 | Hydro-Therapy pools | 117367.62 | 6945594.06 | 117367.62 |  | comp | 2 | 2003-08-11 | 220099.49 | 220099.49 | [8 empty] | 0
| 3 | Sports Floor | 321388 | 7266982.06 | 321388 |  | comp | 3 | 2003-09-02 | 170026.68 | 170026.68 | [8 empty] | 0
| 4 | Dell landscaping WO208818 | 117904 | 7384886.06 | 55302 | 62602 | Comp | 4 | 2003-10-01 | 190250.09 | 190250.09 | [8 empty] | 0
| 5 | General conditons | 1000000 | 8384886.06 | 1000000 |  | comp | 5 | 2003-11-12 | 195143.27 | 195143.27 | [8 empty] | 0
| 6 | Scoreboard Hoist WO 259873 | 189113 | 8573999.06 | 0 | 189113 | comp | 6 | 2003-12-02 | 198651.73 | 198651.73 | [8 empty] | 0
| 7 | Seating | 3348274.75 | 11922273.81 | 3348274.75 |  | comp | 7 | 2004-01-14 | 191951.98 | 191951.98 | [8 empty] | 0
| 8 | Demo for elephant door | 67498 | 11989771.81 | 0 | 67498 | comp | 8 | 2004-02-09 | 229727.17 | 197043.17 | 32684 | [7 empty] | 32684 |  |  | charged
| 9 | Kitchen equipment | 1181989 | 13171760.81 | 0 | 1181989 | comp | 9 | 2004-03-02 | 236799.51 | 236799.51 | [8 empty] | 0
| 10 | Scoreboad, Video, Matrix Display | 4605615 | 17777375.81 | 0 | 4605615 | comp | 10 | 2004-04-05 | 229018.88 | 229018.88 | [8 empty] | 0
| 11 | Audio-Video system | 1073022 | 18850397.81 | 750000 | 323022 | comp | 11 | 2004-05-03 | 245327.26 | 215408.86 | 29918.4 | [7 empty] | 29918.4 |  |  | charged
| 12 | Video Replay System | 813798 | 19664195.81 | 0 | 813798 | comp | 12 | 2004-06-07 | 192748.96 | 192748.96 | [8 empty] | 0
| 13 | General conditons | 1000000 | 20664195.81 | 1000000 |  | comp | 13 | 2004-06-09 | 12744.34 | 12744.34 | [8 empty] | 0
| 14 | Curtain system | 556809 | 21221004.81 | 0 | 556809 | comp | 14 | 2004-07-12 | 233204.5 | 233204.5 | [8 empty] | 0
| 15 | Acoustical baffel system | 284035 | 21505039.81 | 284035 |  | comp | 15 | 2004-08-11 | 249512.83 | 249512.83 | [8 empty] | 0
| 16 | Roller shades | 175700 | 21680739.81 | 175700 |  | comp | 16 | 2004-09-20 | 218983.14 | 218983.14 | [8 empty] | 0
2006-03-07 | 17 | Floor covering | 479725 | 22160464.81 | 389587.86 | 90137.14 | comp | 17 | 2004-10-11 | 213179.77 | 213179.77 | [8 empty] | 0
2006-03-27 | 18 | Backstops, laundry and dock equip | 168859.42 | 22329324.23 | 168859.42 |  | comp | 18 | 2004-11-03 | 274729.81 | 274729.81 | [8 empty] | 0
2006-03-27 | 19 | Electronic changees & WR Floot | 125018.69 | 22454342.92 | 0 | 125018.69 | comp | 19 | 2004-12-06 | 228947.73 | 228947.73 | [8 empty] | 0
2006-03-27 | 20 | Misc caulking | 49999 | 22504341.92 | 49999 | 0 | comp | 20 | 2005-01-12 | 210628.78 | 153894.78 |  |  | 56734 | [5 empty] | 56734
2006-03-27 | 21 | Mark-up on off project costs | 67929 | 22572270.92 | 0 | 67929 | comp | 21 | 2005-01-24 | 118194.8 | 0 |  |  | 118194.8 | [5 empty] | 118194.8
2006-04-10 | 22 | Landscaping | 381249.16 | 22953520.08 | 381249.16 |  | comp | 22 | 2005-02-01 | 260176.26 | 260176.26 | [8 empty] | 0
2006-05-22 | 23 | Camera seats | 42834.75 | 22996354.83 | 42834.75 |  | comp | 23 | 2005-03-08 | 295583.75 | 295583.75 | [8 empty] | 0
2006-05-24 | 24 | specialty lighting | 283691.74 | 23280046.57 | 0 | 283691.74 | comp | 24 | 2005-04-07 | 344304.65 | 344304.65 | [8 empty] | 0
2006-07-05 | 25 | General conditons | 350000 | 23630046.57 | 350000 |  | comp | 25 | 2005-05-09 | 304400.37 | 240277.3 | [5 empty] | 64123.07 |  |  | 64123.07
2006-07-05 | 26 | Parking control gates | 20634.87 | 23650681.44 | 20634.87 |  | comp | 26 | 2005-06-02 | 237934.93 | 237934.93 | [8 empty] | 0
2006-07-05 | 27 | Buckner time sheets | 32223.66 | 23682905.1 | 32223.66 |  | comp | 27 | 2005-07-06 | 222441.62 | 222441.62 | [8 empty] | 0
2006-08-16 | 28 | Install TVs | 27596 | 23710501.1 | 0 | 27596 | comp | 28 | 2005-08-09 | 300045.2 | 300045.2 | [8 empty] | 0
2006-08-21 | 29 | Hall of fame | 343482 | 24053983.1 | 0 | 343482 | comp | 29 | 2005-09-08 | 788078.56 | 275499.22 |  |  | 436703.5 | 75875.84 |  |  |  |  | 512579.34
| 30 | weight room floor | 0 | 24053983.1 | 0 | 0 |  | 30 | 2005-10-10 | 525660.62 | 328648.02 |  |  | 193637.67 |  |  | 3374.93 |  |  | 197012.6
2006-09-19 | 30 | Academic & Practice Courts | 140643 | 24194626.1 | 140643 |  | comp | 31 | 2005-11-07 | 507167.62 | 234488.69 |  |  |  | 272678.93 |  |  |  |  | 272678.93
2006-09-19 | 31 | Misc.-Donor's Suite | 99026.44 | 24293652.54 | 99026.44 |  | comp | 32 | 2005-12-07 | 1608570.54 | 363938.94 |  |  | 1244631.6 | [5 empty] | 1244631.6
2006-09-19 | 32 | Patch & re-paint | 55124.27 | 24348776.81 | 55124.27 |  | comp | 33 | 2006-01-05 | 743406.25 | 379307.95 |  |  | 322729.45 | 41368.85 |  |  |  |  | 364098.3
| 33 | Quality Welding work | 63926.96 | 24412703.77 | 63926.96 |  | comp | 34 | 2006-02-06 | 804048.55 | 659033.57 |  |  |  | 145014.98 |  |  |  |  | 145014.98
| 34 | Team Store | 107002.06 | 24519705.83 | 107002.06 |  | comp | 35 | 2006-03-07 | 595463.86 | 389679.44 |  |  |  | 205784.42 |  |  |  |  | 205784.42
| 35 | Waterproofing on Upper Concourse | 60000 | 24579705.83 | 60000 |  | comp | 36 | 2006-03-08 | 3213453.54 | 1165120.65 |  |  | 1842548.47 | 205784.42 |  |  |  |  | 2048332.89
| 36 | Martin Horn work | 42699.87 | 24622405.7 | 42699.87 |  | comp | 37 | 2006-03-09 | 72996.89 | 72996.89 | [8 empty] | 0
| 37 | Hydro-Therapy pools | 92017.56 | 24714423.26 | 92017.56 |  | comp | 38 | 2006-04-06 | 1940490.87 | 1731669.86 |  |  | 154653.21 | 54167.8 |  |  |  |  | 208821.01
| 38 | Tectum panels, ice machines | 46089.5 | 24760512.76 | 46089.5 |  | comp | 39 | 2006-05-08 | 1991441.78 | 109260 |  |  | 1882181.78 | [5 empty] | 1882181.78
| 39 | Donor's suite, paving | 33101 | 24793613.76 | 33101 |  | comp | 40 | 2006-06-07 | 926296.24 | 801136.56 |  |  |  | 35022.68 | 90137 |  |  |  | 125159.68
2006-12-07 | 40 | Mirrors, handrails, washing pad | 26430.52 | 24820044.28 | 26430.52 |  | comp | 41 | 2006-07-12 | 1191441.23 | 1191441.23 | [8 empty] | 0
2006-12-07 | 41 | Install 2 beams | 45544.7 | 24865588.98 | 45544.7 |  | comp | 42 | 2006-08-15 | 872231.58 | 785754.96 |  |  |  | 73278.62 |  | 13198 |  |  | 86476.62
2006-12-08 | 42 | Press Interview cooridor | 29000 | 24894588.98 | 29000 |  | comp | 43 | 2006-09-12 | 480380.58
2007-01-24 | 43 | Tax rate chg, tvs, floor changes | 30918.14 | 24925507.12 | 30918.14 |  | comp | 44 | 2006-10-08 | 723290.89
2007-02-16 | 44 | Hall of fame | 36965.19 | 24962472.31 | 36965.19 |  | comp | 45 | 2006-11-06 | 571535.83
2007-02-16 | 45 | Misc. painting and drywall | 38090.11 | 25000562.42 | 38090.11 |  | comp | 46 | 2006-12-08 | 479720.28
[8 empty] | 47 | 2007-01-09 | 189343.03
[8 empty] | 48 | 2007-02-07 | 210644.13
[8 empty] | 49 | 2007-03-06 | 176277.01
[8 empty] | 50 | 2007-04-09 | 31934.08
Total |  |  | 18177335.98 | 25000562.42 | 16262261.85 | 8738300.57 | 266.4% |  |  | 24931560.7 | 7567915.29 | 62602.4 | 0 | 6252014.48 | 1035697.92 | 90137 | 67498 | 0 | 0 | 7507949.8
Balance | [9 empty] | 69001.72 | [9 empty] | 0 | -16877335.98
Faulconer - 02 |  | Early Site Work | PO# 269543 | 2059723 | [15 empty] | 15102376.22 | 2118723 | 59000
| 1 | Unsuitable soil Dell | 30465 | 2090188 | 30465 |  | comp | 1 | 2003-05-14 | 140993.4 | 140993.4 | [8 empty] | 0
| 2 | Unsuitable soil Dell waterline | 30816 | 2121004 | 30816 |  | comp | 2 | 2003-06-17 | 119659.91 | 119659.91 | [8 empty] | 0
| 3 | 24 inch storm drain Dell | 36254 | 2157258 | 36254 |  | comp | 3 | 2003-07-16 | 310350.75 | 310350.75 | [8 empty] | 0
| 4 | Perimeter fence at Dell | 25119 | 2182377 | 25119 |  | comp | 4 | 2003-08-06 | 127498.65 | 127498.65 | [8 empty] | 0
| 5 | Unsuit. Soil under foundation Dell | 25146 | 2207523 | 25146 |  | comp | 5 | 2003-09-09 | 159364.31 | 159364.31 | [8 empty] | 0
| 6 | Hardscape changes Dell 208818 | 75525 | 2283048 | 0 | 75525 | comp | 6 | 2003-10-13 | 132163.89 | 132163.89 | [8 empty] | 0
| 7 | Masonry changes Dell | 120411 | 2403459 | 120411 |  | comp | 7 | 2003-11-24 | 391466.52 | 391466.52 | [8 empty] | 0
| 8 | Paving and damage repair Dell | 33600 | 2437059 | 33600 |  | comp | 8 | 2003-12-15 | 248910.26 | 248910.26 | [8 empty] | 0
| 9 | Storm sewer changes - Arena | 13934 | 2450993 | 13934 |  | comp | 9 | 2004-01-19 | 171086.93 | 171086.93 | [8 empty] | 0
| 10 | Additional Dell work | 49441 | 2500434 | 49441 |  | comp | 10 | 2004-02-09 | 102492.85 | 59036.85 | 43456 | [7 empty] | 43456 |  |  | charged
| 11 | Delete landscaping | -49164 | 2451270 | -49164 |  | comp | 11 | 2004-03-15 | 79682.45 | 79682.45 | [8 empty] | 0
| 12 | Storm drain | 23525 | 2474795 | 23525 |  | comp | 12 | 2004-04-06 | 42560.85 | 36925.6 | 5635.25 | [7 empty] | 5635.25 |  |  | charged
| 13 | Misc work at Dell | 16067 | 2490862 | 16067 |  | comp | 13 | 2004-05-14 | 49137.33 | 22703.58 | 26433.75 | [7 empty] | 26433.75 |  |  | no 9/29
| 14 | Work at Biofilter | 54311 | 2545173 | 54311 |  | comp | 14 | 2004-06-09 | 89207.85 | 89207.85 | [8 empty] | 0
| 15 | Emmet St. curbing | 5141 | 2550314 | 5141 |  | comp | 15 | 2004-07-12 | 16055 | 16055 | [8 empty] | 0
| 16 | Credit unit rates | -90900 | 2459414 | -90900 |  | comp | 16 | 2004-08-11 | 20068.75 | 20068.75 | [8 empty] | 0
[8 empty] | 17 | 2004-11-12 | 10497.5 | 10497.5 | [8 empty] | 0
[8 empty] | 18 | 2005-06-08 | 46386.01 | 46386.01
[8 empty] | 19 | 2005-07-07 | 26582.19 | 26582.19
[8 empty] | 20 | 2006-05-08 | 45615.1 | 45615.1
[8 empty] | 21 | 2006-11-06 | 1778.88 | 1778.88
[8 empty] | 22 | 2006-11-06 | 4883.95 | 4883.95
[8 empty] | 23 | 2006-11-06 | 122970.7 | 122970.7
0
Total |  |  | 399691 | 2459414 | 2383889 | 75525 | 19.41% |  |  | 2459414.03 | 2383889.03 | 75525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75525
Balance | [9 empty] | -0.03 | [10 empty] | -340691
Sumter Util - 03 |  | Duct Bank | PO# 290227 | 588000 | [16 empty] | 618000 | 30000
| 1 | Unit rate credit | -28735.18 |  | -28735.18 |  |  | 1 | 2003-08-05 | 61807 | 61807 | [8 empty] | 0
[5 empty] | 0 |  |  | 2 | 2003-08-06 | 167646.5 | 167646.5 | [8 empty] | 0
[5 empty] | 0 |  |  | 3 | 2003-09-09 | 223290.38 | 223290.38 | [8 empty] | 0
[5 empty] | 0 |  |  | 4 | 2003-10-08 | 78557.7 | 78557.7 | [8 empty] | 0
[5 empty] | 0 |  |  | 5 | 2004-08-11 | 27963.24 | 27963.24 | [8 empty] | 0
0
Total |  |  | -28735.18 | 559264.82 | 559264.82 |  | -4.887% |  |  | 559264.82 | 559264.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance | [9 empty] | 0 | [10 empty] | 58735.18 | 0.048869
Cleveland Cem. -04 |  | Park Garage Foundation | PO# 275954 | 1598200 | [16 empty] | 1678200 | 80000
| 1 | Change Foundation Walls | 291000 | 1889200 | 291000 |  | comp | 1 | 2003-08-06 | 283489.5 | 283489.5 | [8 empty] | 0
| 2 | Column and shear wall footings | 174919 | 2064119 | 174919 |  | comp | 2 | 2003-09-09 | 401849.52 | 401849.52 | [8 empty] | 0
| 3 | Change req. ESP-2,4,5 and G-1 | 45660 | 2109779 | 45660 |  | comp | 3 | 2003-10-05 | 228332.5 | 228332.5 | [8 empty] | 0
| 4 | Install embeds and anchor bolts | 30140 | 2139919 | 30140 |  | comp | 4 | 2003-11-24 | 355100.5 | 355100.5 | [8 empty] | 0
| 5 | Unit Rate Credit | -8500 | 2131419 | -8500 |  | comp | 5 | 2004-12-15 | 301791.25 | 301791.25 | [8 empty] | 0
[8 empty] | 6 | 2004-01-19 | 160331.5 | 160331.5 | [8 empty] | 0
[8 empty] | 7 | 2004-02-09 | 40850 | 40850 | [8 empty] | 0
[8 empty] | 8 | 2004-03-15 | 72010 | 72010 | [8 empty] | 0
[8 empty] | 9 | 2004-04-06 | 35625 | 35625 | [8 empty] | 0
[8 empty] | 10 | 2004-05-14 | 94923.05 | 94923.05 | [8 empty] | 0
[8 empty] | 11 | 2004-06-09 | 27550 | 27550 | [8 empty] | 0
[8 empty] | 1-B | 2005-06-08 | 14920.5 | 14920.5 | [8 empty] | 0
[8 empty] | 12 | 2005-06-08 | 8075 | 8075
[8 empty] | 13 | 2005-06-08 | 106570.95 | 106570.95 | [8 empty] | 0
Total |  |  | 533219 | 2131419 | 2131419 |  | 33.36% |  |  | 2131419.27 | 2131419.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance | [9 empty] | -0.27 | [10 empty] | -453219
Faulconer - 05 |  | Arena Sitework | PO# 306970 | 8015000 | [16 empty] | 8415000 | 400000
| 1 | Quad D Underground plumbing | 111773 | 8126773 | 111773 |  | comp | 1 | 2003-10-13 | 240730 | 240730 | [8 empty] | 0
| 2 | Temporary underdrains | 31503 | 8158276 | 31503 |  | comp | 2 | 2003-10-08 | 600020 | 600020 | [8 empty] | 0
| 3 | Stone back fill garage | 133462 | 8291738 | 133462 |  | comp | 3 | 2003-11-18 | 887490 | 887490 | [8 empty] | 0
| 4 | Retaining wall - garage | 449775 | 8741513 | 449775 |  | comp | 4 | 2003-12-15 | 585630.73 | 585630.73 | [8 empty] | 0
| 5 | Manhole #33 | 23860 | 8765373 | 23860 |  | comp | 5 | 2004-01-19 | 175168.98 | 175168.98 | [8 empty] | 0
| 6 | Delete UG work, change MH size | 49542 | 8814915 | 49542 |  | Comp | 6 | 2004-02-09 | 65422.94 | 65422.94 | [8 empty] | 0
| 7 | Rock excavation at HH line | 27476 | 8842391 | 27476 |  | comp | 7 | 2004-03-15 | 235282.94 | 235282.94 | [8 empty] | 0
| 8 | Finish grading Feb. 2004 | 29251 | 8871642 | 29251 |  | comp | 8 | 2004-04-06 | 336032.77 | 336032.77 | [8 empty] | 0
| 9 | Foundation Rock Excavation | 48463 | 8920105 | 48463 |  | comp | 9 | 2004-05-14 | 143644.75 | 143644.75 | [8 empty] | 0
| 10 | Unsuit Soil at Mech Plant 249331 | 49886 | 8969991 | 0 | 49886 | comp | 10 | 2004-06-09 | 182855.91 | 132989.91 |  | 49866 | [6 empty] | 49866 |  |  | charged
2006-04-10 | 11 | Misc temp stone const. | 45286 | 9015277 | 45286 |  | comp | 11 | 2004-07-12 | 40300.23 | 40300.23 | [8 empty] | 0
2006-04-10 | 12 | Relocation of water mains | 48431 | 9063708 | 48431 |  | comp | 12 | 2004-08-11 | 146301.71 | 146301.71 | [8 empty] | 0
2006-04-10 | 13 | Temp ramps and roads and remova; | 44031 | 9107739 | 44031 |  | comp | 13 | 2004-09-13 | 39679.6 | 39679.6 | [8 empty] | 0
2006-04-10 | 14 | Revise landscape and plaza | 3148 | 9110887 | 3148 |  | comp | 14 | 2004-10-13 | 165851 | 165851 | [8 empty] | 0
| 15 | Change Request Site 12 | 49937 | 9160824 | 49937 |  | comp | 15 | 2004-11-12 | 53048 | 53048 | [8 empty] | 0
| 16 | Credit unit rates | -59576 | 9101248 |  |  | comp | 16 | 2004-12-06 | 188556 | 188556 | [8 empty] | 0
| 17 | COR-45 | 45738 | 9146986 |  |  | comp | 17 | 2005-01-12 | 283522.75 | 283522.75 | [8 empty] | 0
| 18 | PG Stripping | 35012 | 9181998 |  |  | comp | 18 | 2005-02-07 | 248273 | 248273
| 19 | Credit unit rates | -84900 | 9097098 |  |  | comp | 19 | 2005-03-08 | 295668.5 | 295668.5
| 20 | Grading, curbing & Asphalt | 32935.5 | 9130033.5 |  |  | comp | 20 | 2005-04-06 | 80471.65 | 80471.65 | [8 empty] | 0
| 21 | Pave Service Drive | 47468 | 9177501.5 |  |  | comp | 21 | 2005-05-10 | 146858.6 | 146858.6
| 22 | Misc. Cleanup | 1676.34 | 9179177.84 |  |  | comp | 22 | 2005-06-08 | 303040.5 | 303040.5
[8 empty] | 23 | 2005-07-07 | 117396.25 | 117396.25
[8 empty] | 24 | 2005-08-09 | 93328 | 93328
[8 empty] | 25 | 2005-09-08 | 166055.25 | 166055.25
[8 empty] | 26 | 2005-10-11 | 178999 | 178999
[8 empty] | 27 | 2005-11-08 | 176853.9 | 176853.9
[8 empty] | 28 | 2005-12-12 | 162568.75 | 162568.75
[8 empty] | 29 | 2006-01-09 | 216861.25 | 216861.25
[8 empty] | 30 | 2006-02-07 | 154327.5 | 154327.5
[8 empty] | 31 | 2006-03-08 | 119609.75 | 119609.75
[8 empty] | 32 | 2006-04-10 | 180785 | 180785
[8 empty] | 33 | 2006-05-08 | 471447.57 | 471447.57
[8 empty] | 34 | 2006-06-07 | 644290 | 644290
[8 empty] | 35 | 2006-07-12 | 175883 | 175883
[8 empty] | 36 | 2006-08-14 | 140362.88 | 140362.88
[8 empty] | 37 | 2006-09-08 | 42921 | 42921
[8 empty] | 38 | 2006-10-09 | 89623 | 89623
[8 empty] | 39 | 2006-11-06 | 145056.3 | 145056.3
[8 empty] | 40 | 2006-11-30 | 458958.89 | 458958.89
Total |  |  | 1164177.84 | 9179177.84 | 9129291.84 | 49886 | 14.52% |  |  | 9179177.85 | 9129311.85 | 0 | 49866 | 0 | 0 | 0 | 0 | 0 | 0 | 49866
Balance | [9 empty] | -0.01 | [10 empty] | -764177.84
Shockey Precast -06 |  | Structural Precast | PO#317105 | 5927448 | [16 empty] | 6227448 | 300000
| 1 | Stair tower change | 41837 | 5969285 | 41837 |  | comp | 1 | 2003-11-25 | 72359 | 72359 | [8 empty] | 0
| 2 | Credit for steps | -252747 | 5716538 | -252747 |  | comp | 2 | 2004-01-19 | 80463 | 80463 | [8 empty] | 0
| 3 | Mechanical Plant 249331 | 638195 | 6354733 | 0 | 638195 | comp | 3 |  | 19586 | 19586 | [8 empty] | 0
| 4 | Walls behind row #7 Upper | 57603 | 6412336 | 57603 |  | comp | 4 | 2004-03-15 | 34169 | 34169 | [8 empty] | 0
| 5 | Embeds and inserts in Addendum 1 | 47380 | 6459716 | 47380 |  | comp | 5 | 2004-04-06 | 101530 | 101530 | [8 empty] | 0
| 6 | Change tubs,spandrels and s. blast | 40484 | 6500200 | 40484 |  | comp | 6 | 2004-05-14 | 112288 | 112288 | [8 empty] | 0
| 7 | Changes for elephant door | 24869 | 6525069 | 0 | 24869 | comp | 7 | 2004-06-09 | 310999 | 310999 | [8 empty] | 0
| 8 | Misc. Repairs | 10954 | 6536023 |  |  | comp | 8 | 2004-07-12 | 516055 | 516055 | [8 empty] | 0
| 9 | Credit for unused units | -55420 | 6480603 |  |  | comp | 9 | 2004-08-11 | 484368 | 484368 | [8 empty] | 0
[8 empty] | 10 | 2004-09-13 | 1241273 | 922175 |  | 319098 | [6 empty] | 319098 |  |  | no 9/29
[8 empty] | 11 | 2004-10-13 | 1712837 | 1393739 |  | 319098 | [6 empty] | 319098
[8 empty] | 12 | 2004-11-12 | 727844 | 727844 | [8 empty] | 0
[8 empty] | 13 | 2004-12-06 | 216878 | 216878 | [8 empty] | 0
[8 empty] | 14 | 2005-01-12 | 198597 | 198597 | [8 empty] | 0
[8 empty] | 15 | 2005-02-07 | 218867 | 218867 | [8 empty] | 0
[8 empty] | 16 | 2005-06-08 | 55077 | 30208 | [5 empty] | 24869 |  |  | 24869
[8 empty] | 17 | 2005-10-11 | 30046 | 30046
[8 empty] | 18 | 2006-09-21 | 23336 | 23336
[8 empty] | 19 | 2006-09-21 | 324030 | 324030
Total |  |  | 553155 | 6480603 | 5817539 | 663064 | 9.332% |  |  | 6480602 | 5440125 | 0 | 638196 | 0 | 0 | 0 | 24869 | 0 | 0 | 663065
Balance | [9 empty] | 1 | [10 empty] | -253155
Cleveland Cem. -07 |  | CIP Concrete | PO# 314843 | 10193300 | [16 empty] | 10693300 | 500000
| 1 | CIP for tie beam | 27792 | 10221092 | 27792 |  | Comp | 1 | 2003-11-25 | 108015 | 108015 | [8 empty] | 0
| 2 | CIP for COR#4,6,12, and 15 | 47112 | 10268204 | 47112 |  | Comp | 2 | 2003-12-15 | 348944.5 | 348944.5 | [8 empty] | 0
| 3 | Change request ASP # 1 | 78500 | 10346704 | 78500 |  | Comp | 3 | 2004-01-19 | 333280.9 | 333280.9 | [8 empty] | 0
| 4 | CR ASP -3 and RFI -121 | 64500 | 10411204 | 64500 |  | Comp | 4 | 2004-02-09 | 854773.9 | 854773.9 | [8 empty] | 0
| 5 | CR ASP -4 | 40389 | 10451593 | 40389 |  | Comp | 5 | 2004-03-15 | 877314.55 | 877314.55 | [8 empty] | 0
| 6 | Conc walls at 3 elevators | 76000 | 10527593 | 76000 |  | Comp | 6 | 2004-04-06 | 1047713.2 | 1047713.2 | [8 empty] | 0
| 7 | CIP for Mech Plant 249331 | 448992 | 10976585 | 0 | 448992 | Comp | 7 | 2004-05-14 | 1184840.95 | 1184840.95 | [8 empty] | 0
| 8 | Overtime to expidite | 44342 | 11020927 | 44342 |  | Comp | 8 | 2004-06-09 | 1043223.5 | 1043223.5 | [8 empty] | 0
| 9 | Misc conc. And rails | 35490 | 11056417 | 35490 |  | Comp | 9 | 2004-07-12 | 1170509.25 | 1170509.25 | [8 empty] | 0
| 10 | Slab on grade | 476004 | 11532421 | 476004 |  | Comp | 10 | 2004-08-11 | 721457.55 | 721457.55 | [8 empty] | 0
| 11 | ESP-10 pilaster in garage | 10675 | 11543096 | 10675 |  | Comp | 11 | 2004-09-13 | 1136665.5 | 1136665.5 | [8 empty] | 0
| 12 | GSP concrete work | 29680 | 11572776 | 29680 |  | Comp | 12 | 2004-10-13 | 593442.88 | 279148.48 |  | 314294.4 | [6 empty] | 314294.4
| 13 | ASP-9 Hydro-therapy pit | 29450 | 11602226 | 29450 |  | Comp | 13 | 2004-11-12 | 231493.72 | 96796.12 |  | 134697.6 | [6 empty] | 134697.6
| 14 | ASP-7 changes in depressed slab | 34426 | 11636652 | 34426 |  | Comp | 14 | 2004-12-06 | 439825 | 439825 | [8 empty] | 0
| 15 | ESP-8 | 45900 | 11682552 | 45900 |  | comp | 15 | 2005-01-12 | 128055.63 | 128055.63 | [8 empty] | 0
| 16 | RFI 560 | 36095 | 11718647 | 36095 |  | comp | 16 | 2005-02-07 | 49674.55 | 49674.55 | [8 empty] | 0
| 17 | Install new steel embeds | 47100 | 11765747 | 47100 |  | comp | 17 | 2005-03-09 | 151056.65 | 151056.65
| 18 | Install temporary guardrails | 21812 | 11787559 | 21812 |  | comp | 18 | 2005-04-06 | 102196.25 | 102196.25
| 19 | Install additional aisle steps | 23360 | 11810919 | 23360 |  | comp | 19 | 2005-05-10 | 9761.25 | 9761.25
| 20 | Patch damaged concrete | 33550 | 11844469 | 33550 |  | comp | 20 | 2005-06-08 | 214244.57 | 214244.57
| 21 | Install changes atGrand staircases | 21250 | 11865719 | 21250 |  | comp | 21 | 2005-07-07 | 189453.75 | 189453.75
| 22 | Install CIP slab between risers | 71830 | 11937549 | 71830 |  | comp | 22 | 2005-08-09 | 40280 | 40280
| 23 | Concrete slab for Elephant door | 36800 | 11974349 | 36800 |  | comp | 23 | 2006-01-11 | 146395 | 146395
| 24 | Install steel inserts in the Event level | 44634 | 12018983 | 44634 |  | comp | 24 | 2006-01-11 | 103198.5 | 103198.5
| 25 | Change Request AP15, RFI 681, ASP 18 | 34074 | 12053057 | 34074 |  | comp | 25 | 2006-01-11 | 132646.6 | 132646.6
| 26 | Practice Facility Changes | 44680 | 12097737 | 44680 |  | comp | 26 | 2006-03-08 | 81509.62 | 81509.62
| 27 | RFI 1102 | 15340 | 12113077 | 15340 |  | comp | 27 | 2006-05-10 | 118404.2 | 118404.2
| 28 | ASP-7 & AP-34 | 439998 | 12553075 | 439998 |  | comp | 28 | 2006-06-07 | 125399.43 | 125399.43
| 29 | Credit for deleting tie beams | -95363 | 12457712 | -95363 |  | comp | 29 | 2006-07-12 | 87400 | 87400
2007-01-24 | 30 | Credit for unused units | -67000 | 12390712 | -67000 |  | comp | 30 | 2006-09-08 | 619535.6 | 619535.6
Total |  |  | 2197412 | 12390712 | 11941720 | 448992 | 21.56% |  |  | 12390712 | 11941720 | 0 | 448992 | 0 | 0 | 0 | 0 | 0 | 0 | 448992
Balance | [9 empty] | 0 | [10 empty] | -1697412
Hirschfeld Steel -08 |  | Structural Steel | PO# 321203 | 6695080 | [16 empty] | 6995080 | 300000
| 1 | Struc Steel ASP 3,4 and 8 | 49333 | 6744413 | 49333 |  | Comp | 1 | 2004-05-14 | 298314.25 | 298314.25 | [8 empty] | 0
| 2 | Struc Steel RFI 222 &304 | 42867 | 6787280 | 42867 |  | Comp | 2 | 2004-06-09 | 161533.25 | 161533.25 | [8 empty] | 0
| 3 | Struc Steel RFI 152 | 48712 | 6835992 | 48712 |  | Comp | 3 | 2004-07-13 | 622454.53 | 622454.53 | [8 empty] | 0
| 4 | Struc Steel ASP 4 & RFI's | 45109 | 6881101 | 45109 |  | Comp | 4 | 2004-08-11 | 761646.97 | 761646.97 | [8 empty] | 0
| 5 | Additional Detailing | 49500 | 6930601 | 49500 |  | Comp | 5 | 2004-09-13 | 667156.26 | 667156.26 | [8 empty] | 0
| 6 | Change tie beam to steel | 195339 | 7125940 | 195339 |  | Comp | 6 | 2004-10-13 | 121202.43 | 121202.43 | [8 empty] | 0
| 7 | Struc Steel ASP 5 | 157568 | 7283508 | 157568 |  | Comp | 7 | 2004-11-12 | 865811.1 | 865811.1 | [8 empty] | 0
| 8 | Struc Steel ASP 1 | 74493 | 7358001 | 74493 |  | Comp | 8 | 2004-12-06 | 1313213.36 | 1313213.36 | [8 empty] | 0
| 9 | DCN 25,27,28,32,33,41 | 33152 | 7391153 | 33152 |  | Comp | 9 | 2005-01-12 | 895096.5 | 895096.5 | [8 empty] | 0
| 10 | DCN 34,38,40,45 | 35054 | 7426207 | 35054 |  | Comp | 10 | 2005-02-07 | 431523.62 | 431523.62 | [8 empty] | 0
| 11 | DCN 36,46,47,48,50,61 | 31936 | 7458143 | 31936 |  | Comp | 11 | 2005-03-08 | 240494.4 | 240494.4
| 12 | Relocate rigging beams | 19827 | 7477970 | 19827 |  | Comp | 12 | 2005-04-06 | 218596.67 | 218596.67
2006-03-01 | 13 | DCN 30,59,65,67,71 | 38151 | 7516121 | 38151 |  | Comp | 13 | 2005-05-10 | 113251.4 | 113251.4
2006-03-01 | 14 | DCN31,49,60,64,69,70 | 29539 | 7545660 | 29539 |  | Comp | 14 | 2005-06-08 | 166854.17 | 166854.17 | [8 empty] | 0
2006-03-01 | 15 | DCN 72,73,77,78 | 43334 | 7588994 | 43334 |  | Comp | 15 | 2005-07-07 | 78480.45 | 78480.45
2006-03-01 | 16 | DCN 79,80,81.84 | 25539 | 7614533 | 25539 |  | Comp | 16 | 2005-08-09 | 29181.62 | 29181.62
2006-03-01 | 17 | DCN 44,46,86,87,88 | 36212 | 7650745 | 36212 |  | Comp | 17 | 2005-10-11 | 131678.02 | 131678.02
2006-03-07 | 18 | DCN 76 and 92 | 248748 | 7899493 | 248748 |  | Comp | 18 | 2005-11-08 | 93491.4 | 93491.4
2006-03-27 | 19 | DCN 90,91,58,89 | 16898 | 7916391 | 16898 |  | Comp | 19 | 2006-01-09 | 269619.5 | 269619.5
| 20 | Credit for unused unit rates | -25080 | 7891311 | -25080 |  | Comp | 20 | 2006-03-09 | 18845.6 | 18845.6
[8 empty] | 21 | 2006-04-10 | 197282.78 | 197282.78
[8 empty] | 22 | 2006-08-29 | 23826 | 23826
[8 empty] | 23 | 2006-09-21 | 173457.3 | 173457.3
Total |  |  | 1196231 | 7891311 | 7891311 |  | 17.87% |  |  | 7893011.58 | 7719554.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance | [9 empty] | -1700.58 | [10 empty] | -896231
Shockey Precast- 09 |  | Arch Precast Conc | PO#348890 | 1318197 | [16 empty] | 1383197 | 65000
| 1 | Site Walls | 448500 | 1766697 | 448500 |  | Comp | 1 | 2004-05-14 | 12491 | 12491 | [8 empty] | 0
| 2 | Changes to precast site walls | 23483 | 1790180 | 23483 |  | Comp | 2 | 2004-05-14 | 12873 | 12873 | [8 empty] | 0
| 3 | Precast coping stones | 42481 | 1832661 | 42481 |  | Comp | 3 | 2004-06-09 | 35831 | 35831 | [8 empty] | 0
| 4 | Add lettering to panels | 48146 | 1880807 | 48146 |  | Comp | 4 | 2004-07-12 | 21694 | 21694 | [8 empty] | 0
[5 empty] | 0 |  |  | 5 | 2004-08-11 | 69477 | 69477 | [8 empty] | 0
[5 empty] | 0 |  |  | 6 | 2004-09-13 | 62340 | 62340 | [8 empty] | 0
[5 empty] | 0 |  |  | 7 | 2004-10-13 | 122790 | 122790 | [8 empty] | 0
[8 empty] | 8 | 2004-11-12 | 189519 | 189519 | [8 empty] | 0
[8 empty] | 9 | 2004-12-06 | 254325 | 254325 | [8 empty] | 0
[8 empty] | 10 | 2005-01-12 | 167635 | 167635 | [8 empty] | 0
[8 empty] | 11 | 2005-02-15 | 96642 | 96642 | [8 empty] | 0
[8 empty] | 12 | 2005-03-08 | 94316 | 94316
[8 empty] | 13 | 2005-04-06 | 71993 | 71993
[8 empty] | 14 | 2005-05-10 | 18373 | 18373
[8 empty] | 15 | 2005-06-08 | 36814 | 36814
[8 empty] | 16 | 2005-07-07 | 71129 | 71129
[8 empty] | 17 | 2005-08-09 | 89239 | 89239
[8 empty] | 18 | 2005-09-08 | 80692 | 80692
[8 empty] | 19 | 2005-10-11 | 3407 | 3407
[8 empty] | 20 | 2005-11-08 | 43310 | 43310
[8 empty] | 21 | 2005-12-12 | 57447 | 57447
[8 empty] | 22 | 2006-01-09 | 131105 | 131105
[8 empty] | 23 | 2006-03-08 | 16783 | 16783
[8 empty] | 24 | 2006-09-21 | 26541 | 26541
[8 empty] | 25 | 2006-09-21 | 94040 | 94040
Total |  |  | 562610 | 1880807 | 1880807 |  | 42.68% |  |  | 1880806 | 1880806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance | [9 empty] | 1 | [10 empty] | -497610
Thyssen Krupp -10 |  | Elevators | PO#406947 | 599017 | [16 empty] | 628017 | 29000
| 1 | Overtime and cleaning | 44913.48 | 643930.48 | 44913.48 |  | Comp | 1 | 2005-11-08 | 407720.05 | 407720.05 | [8 empty] | 0
2007-01-24 | 2 | Misc. repairs | 3008 | 646938.48 | 3008 |  | Comp | 2 | 2006-07-12 | 161346.1 | 161346.1 | [8 empty] | 0
|  |  |  | 0 |  |  |  | 3 | 2006-07-12 | 44913 | 44913 | [8 empty] | 0
Total |  |  | 47921.48 | 646938.48 | 646938.48 |  | 8% |  |  | 613979.15 | 613979.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance | [9 empty] | 32959.33 | [10 empty] | -18921.48
Bat Masonry - 11 |  | Masonry | PO#378144 | 4295000 | [16 empty] | 4495000 | 200000
2006-04-03 | 1 | Misc Masonry CR 1-18 | 20291 | 4315291 | 20291 |  | Comp | 1 | 2004-08-18 | 72897.82 | 72897.82 | [8 empty] | 0
2006-04-03 | 2 | AP-32 | 25100 | 4340391 | 25100 |  | Comp | 2 | 2004-09-13 | 125538.89 | 121488.89 | [7 empty] | 4050 | 4050
2006-04-03 | 3 | CR 19-29 | 29401 | 4369792 | 25351 | 4050 | Comp | 3 | 2004-10-13 | 228618.69 | 228618.69 | [8 empty] | 0
| 4 | Stone Veneer biofilter walls | 325000 | 4694792 | 325000 |  | Comp | 4 | 2004-11-12 | 367942.6 | 367942.6 | [8 empty] | 0
2007-01-24 | 5 | Misc. T&M tickets | 47455.35 | 4742247.35 | 47455.35 |  | Comp | 5 | 2004-12-06 | 276078.5 | 276078.5 | [8 empty] | 0
2007-02-20 | 6 | Misc. T&M tickets | 6470.48 | 4748717.83 | 6470.48 |  | Comp | 6 | 2005-01-12 | 496370.49 | 496370.49 | [8 empty] | 0
[5 empty] | 0 |  |  | 7 | 2005-02-07 | 94939.44 | 94939.44 | [8 empty] | 0
[5 empty] | 0 |  |  | 8 | 2005-03-08 | 158706.05 | 158706.05 | [8 empty] | 0
[5 empty] | 0 |  |  | 9 | 2005-04-06 | 239115.52 | 239115.52 | [8 empty] | 0
[5 empty] | 0 |  |  | 10 | 2005-05-10 | 299528.49 | 299528.49 | [8 empty] | 0
[5 empty] | 0 |  |  | 11 | 2005-06-08 | 220437.29 | 220437.29 | [8 empty] | 0
[5 empty] | 0 |  |  | 12 | 2005-07-07 | 138795.52 | 138795.52 | [8 empty] | 0
[5 empty] | 0 |  |  | 13 | 2005-08-09 | 210279.65 | 210279.65 | [8 empty] | 0
[5 empty] | 0 |  |  | 14 | 2005-09-12 | 184775.09 | 184775.09 | [8 empty] | 0
[5 empty] | 0 |  |  | 15 | 2005-10-11 | 232202.42 | 232202.42 | [8 empty] | 0
[5 empty] | 0 |  |  | 16 | 2005-11-08 | 245393.31 | 245393.31 | [8 empty] | 0
[5 empty] | 0 |  |  | 17 | 2005-12-12 | 228397.1 | 228397.1 | [8 empty] | 0
[8 empty] | 18 | 2006-01-09 | 198540.17 | 198540.17 | [8 empty] | 0
[8 empty] | 19 | 2006-02-07 | 61692.95 | 61692.95 | [8 empty] | 0
[8 empty] | 20 | 2006-04-10 | 126627.4 | 126627.4 | [8 empty] | 0
[8 empty] | 21 | 2006-05-10 | 21612.5 | 17562.5 | [7 empty] | 4050 | 4050
[8 empty] | 22 | 2006-06-07 | 77187.5 | 77187.5
[8 empty] | 23 | 2006-07-12 | 61750 | 61750
[8 empty] | 24 | 2006-08-14 | 61750 | 61750
[8 empty] | 25 | 2006-09-08 | 116557.3 | 116557.3
[8 empty] | 26 | 2007-01-08 | 31687.5 | 31687.5
[8 empty] | 27 | 2007-01-08 | 117369.8 | 117369.8
[8 empty] | 28 | 2007-01-26 | 53925.83 | 53925.83
Total |  |  | 453717.83 | 4748717.83 | 4744667.83 | 4050 | 10.56% |  |  | 4748717.82 | 4740617.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8100 | 0
Balance | [9 empty] | 0.01 | [10 empty] | -253717.83
Roof Services Corp12 |  | Roofing | PO# 373407 | 1320760 | [16 empty] | 1386760 | 66000
| 1 | Additional Temp roofing and repairs | 26186.36 | 1346946.36 |  |  | Comp | 1 | 2004-12-06 | 50787.95 | 50787.95 | [8 empty] | 0
2006-05-16 | 2 | Misc roof repair | 4154.83 | 1351101.19 | 4154.83 |  | Comp | 2 | 2005-01-12 | 224747.2 | 224747.2 | [8 empty] | 0
| 3 | Roof inspection, repairs | 4324.29 | 1355425.48 | 4324.29 |  | Comp | 3 | 2005-02-07 | 34684.5 | 34684.5 | [8 empty] | 0
|  |  |  | 1355425.48 | 0 |  |  | 4 | 2005-03-08 | 170729.25 | 170729.25
[5 empty] | 0 |  |  | 5 | 2005-04-06 | 259017.5 | 259017.5
[5 empty] | 0 |  |  | 6 | 2005-05-10 | 121635.63 | 121635.63
[5 empty] | 0 |  |  | 7 | 2005-06-08 | 62787.88 | 62787.88
[5 empty] | 0 |  |  | 8 | 2005-07-07 | 33729.75 | 33729.75
[5 empty] | 0 |  |  | 9 | 2005-10-11 | 48098.5 | 48098.5
[5 empty] | 0 |  |  | 10 | 2005-11-08 | 74261.5 | 74261.5
[5 empty] | 0 |  |  | 11 | 2005-12-12 | 47975 | 47975
[8 empty] | 12 | 2006-01-09 | 76462.04 | 76462.04
[8 empty] | 13 | 2006-02-07 | 65917.65 | 65917.65
[8 empty] | 14 | 2006-03-08 | 7600 | 7600
[8 empty] | 15 | 2006-07-12 | 5111.79 | 5111.79
[8 empty] | 16 | 2006-11-06 | 4108.08 | 4108.08
[8 empty] | 17 | 2006-11-06 | 33885.64 | 33885.64
[8 empty] | 18 | 2006-12-06 | 33885.62 | 33885.62
Total |  |  | 34665.48 | 1355425.48 | 1355425.48 |  | 2.625% |  |  | 1355425.48 | 1355425.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance | [9 empty] | 0 | [10 empty] | 31334.52
Colonical Mech -13 |  | Mech and Plumb | PO# 343945 | 11210500 | [16 empty] | 11760500 | 550000
| 1 | Central Plant UG Plumbing | 68618 | 11279118 | 68618 |  | Comp | 1 | 2004-03-29 | 128250 | 128250 | [8 empty] | 0
| 2 | West end infrastructure | 138378 | 11417496 | 138378 |  | Comp | 2 | 2004-03-29 | 410454.15 | 410454.15 | [8 empty] | 0
| 3 | MEP-5 Add 3 toilet rooms | 42004 | 11459500 | 42004 |  | Comp | 3 | 2004-04-06 | 367445.75 | 367445.75 | [8 empty] | 0
| 4 | MEP-2 ASBO changes | 163832 | 11623332 | 163832 |  | Comp | 4 | 2004-05-14 | 198952.06 | 198952.06 | [8 empty] | 0
| 5 | Overtime for Quads A and B | 27532 | 11650864 | 27532 |  | Comp | 5 | 2004-06-09 | 271791.15 | 271791.15 | [8 empty] | 0
| 6 | Gas meters on boilers | 25348 | 11676212 | 25348 |  | Comp | 6 | 2004-07-13 | 589784.22 | 589784.22 | [8 empty] | 0
| 7 | Install Low NOX burners | 58106 | 11734318 | 58106 |  | Comp | 7 | 2004-08-11 | 590321.48 | 590321.48 | [8 empty] | 0
| 8 | Add by-pass at cooling towers | 101048 | 11835366 | 101048 |  | Comp | 8 | 2004-09-13 | 409857.96 | 409857.96 | [8 empty] | 0
| 9 | MEP -9 revisions | 75742 | 11911108 | 75742 |  | Comp | 9 | 2004-10-13 | 814429.1 | 814429.1 | [8 empty] | 0
| 10 | VE items deduct | -111094 | 11800014 | -111094 |  | Comp | 10 | 2004-11-12 | 1899890.48 | 1899890.48 | [8 empty] | 0
| 11 | Galvanize pipe sleeves in Plant | 1804 | 11801818 | 1804 |  | Comp | 11 | 2004-12-06 | 948471.46 | 948471.46 | [8 empty] | 0
| 12 | Core drilling for garage drains | 11074 | 11812892 | 11074 |  | Comp | 12 | 2005-01-12 | 765495.42 | 765495.42 | [8 empty] | 0
| 13 | Relocate fuel oil pumps | 29828 | 11842720 | 29828 |  | Comp | 13 | 2005-02-07 | 717001.22 | 717001.22 | [8 empty] | 0
| 14 | MEP-14 Non west space | 61840 | 11904560 | 61840 |  | Comp | 14 | 2005-03-08 | 854229.77 | 854229.77
| 15 | Boiler breeching wind load calcs. | 3927 | 11908487 | 3927 |  | Comp | 15 | 2005-04-06 | 220275.6 | 220275.6
| 16 | MEP-19 Misc. cliller plant revisions | 23741 | 11932228 | 23741 |  | Comp | 16 | 2005-05-10 | 503956.81 | 503956.81
| 17 | Wesr end fit-out | 660263 | 12592491 | 0 | 660263 | Comp | 17 | 2005-06-08 | 399540.49 | 135435.29 |  |  |  |  | 264105.2 |  |  |  | 264105.2
| 18 | Warranty extension - Arena | 46900 | 12639391 | 46900 |  | Comp | 18 | 2005-07-07 | 446874.11 | 316813.11 |  |  |  |  | 130061 |  |  |  | 130061
| 19 | Warranty extension - Boiler/Chiller | 48900 | 12688291 | 48900 |  | Comp | 19 | 2005-08-09 | 351754.03 | 192557.18 |  |  |  |  | 159196.85 |  |  |  | 159196.85
| 20 | Academic center | 117318 | 12805609 | 0 | 117318 | Comp | 20 | 2005-09-08 | 259782.79 | 209686.63 |  |  |  |  | 50096.16 |  |  |  | 50096.16
| 21 | Boiler stack testing | 19532 | 12825141 | 0 | 19532 | Comp | 21 | 2005-10-11 | 224146.07 | 163569.83 |  |  |  |  | 60576.24 |  |  |  | 60576.24
2006-03-01 | 22 | MEP 32,34,35 and 36 | 40392 | 12865533 | 32728 | 7664 | Comp | 22 | 2005-11-08 | 125356.29 | 125356.29 | [8 empty] | 0
2006-03-01 | 23 | Boiler stack NOX testing | 16100 | 12881633 | 0 | 16100 | Comp | 23 | 2005-12-12 | 128725.53 | 118784.78 |  |  |  |  | 9940.75 |  |  |  | 9940.75
2006-03-01 | 24 | Rework duct in Quads A&D conflicts | 36286 | 12917919 | 36286 |  | Comp | 24 | 2006-01-09 | 155532.6 | 94446.85 |  |  |  |  | 61085.75 |  |  |  | 61085.75
2006-03-01 | 25 | SMG changes to locker rm , Laundry | 11382 | 12929301 | 0 | 11382 | Comp | 25 | 2006-02-07 | 215864.95 | 152276.1 |  | 26599.4 |  |  | 36989.45 |  |  |  | 63588.85
2006-02-22 | 26 | womens coaches locker | 48797 | 12978098 | 48797 |  | Comp | 26 | 2006-03-08 | 154171.58 | 114993.98 |  | 28269.6 |  |  |  | 10908 |  |  | 39177.6
2006-04-03 | 27 | Install hot tubs | 34432 | 13012530 | 34432 |  | Comp | 27 | 2006-04-10 | 90093.23 | 86459.23 |  |  |  |  | 3634 |  |  |  | 3634
2006-04-03 | 28 | Add stack testing &oil piping | 23306 | 13035836 | 4069 | 19237 | Comp | 28 | 2006-05-10 | 286371.97 | 280469.12 |  |  |  |  | 5428.85 | 474 |  |  | 5902.85
2006-06-06 | 29 | Change duct work insulation | 31843 | 13067679 | 31843 |  | Comp | 29 | 2006-06-07 | 47125.84 | 46063.54 |  |  |  |  | 588.3 | 474 |  |  | 1062.3
2006-06-28 | 30 | Relocate controls for roof fan disconects | 56642 | 13124321 | 56642 |  | Comp | 30 | 2006-08-29 | 53276 | 53276
2006-06-28 | 31 | Overtime for HVAC start-up | 113561 | 13237882 | 113561 |  | Comp | 31 | 2006-09-21 | 394229.25 | 394229.25
| 32 | Hook-up hot tubs | 12036 | 13249918 | 12036 |  | Comp | 32 | 2006-11-06 | 267871.05 | 267871.05
| 33 | Kitchen work | 67131 | 13317049 | 67131 |  | Comp | 33 | 2006-11-30 | 42684.98 | 42684.98
| 34 | OT - March 2006-July 2006 | 53791 | 13370840 | 53791 |  | Comp | 34 | 2007-01-08 | 80700.72 | 80700.72
| 35 | Smoke Control Mode Changes | 23586 | 13394426 | 23586 |  | Comp | 35 | 2007-03-06 | 36561.66 | 36561.66
| 36 | Backcharge for Halo scaffold | -35000 | 13359426 | -35000 |  | Comp | 36 | 2007-03-06 | 115269.24 | 115269.24
| 37 | Add fire dampers | 37639 | 13397065 | 37639 |  | Comp | 37 | 2007-03-21 | 57175.2 | 57175.2
| 38 | Fan Airflow change | 29086 | 13426151 | 29086 |  | Comp | 38 | 2007-03-21 | 55231.8 | 55231.8
| 39 | Replace damanged fan parts | 32933 | 13459084 | 32933 |  | Comp
| 40 | Team Store, Coffee Bar | 25366 | 13484450 | 25366 |  | Comp
| 41 | Ice Machine | 13256 | 13497706 | 13256 |  | Comp
2007-01-24 | 42 | Relocate fan in Quad B | 76342 | 13574048 | 76342 |  | Comp
2007-03-21 | 43 | Boiler Stack Testing, Sump Alarm | 49531 | 13623579 | 49531 |  | Comp
2007-03-21 | 44 | Modifications ti AHU 101-104 | 12000 | 13635579 | 12000 |  | Comp
2007-03-21 | 45 | Changes to Hydronic piping | 45367 | 13680946 | 45367 |  | Comp
Total |  |  | 2470446 | 13680946 | 12829450 | 851496 | 22.04% |  |  | 13678946.01 | 12830518.46 | 0 | 54869 | 0 | 0 | 781702.55 | 11856 | 0 | 0 | 836571.55
Balance | [9 empty] | 1999.99 | [10 empty] | -1920446
Design Electric- 14 |  | Electrical | PO# 333364 | 6680640 | [16 empty] | 7010640 | 330000
| 1 | West Pergola Light Fixtures | 14277.69 | 6694917.69 | 14277.69 |  | Comp | 1 | 2004-02-09 | 206087.3 | 206087.3 | [8 empty] | 0
| 2 | Overtime for UG Quad C&D | 19838.04 | 6714755.73 | 19838.04 |  | Comp | 2 | 2004-02-09 | 115330 | 115330 | [8 empty] | 0
| 3 | Park Garage CR-G1 (2/10/04) | 28058 | 6742813.73 | 28058 |  | comp | 3 | 2004-03-15 | 146428.25 | 146428.25 | [8 empty] | 0
| 4 | Changes to 15 KV Feeders | 42501 | 6785314.73 | 42501 |  | Comp | 4 | 2004-04-06 | 225239.3 | 225239.3 | [8 empty] | 0
| 5 | Service for food service | 27761 | 6813075.73 | 27761 |  | Comp | 5 | 2004-05-14 | 156750 | 156750 | [8 empty] | 0
| 6 | Relocate motor feeds RFI 794 | 37560 | 6850635.73 | 37560 |  | Comp | 6 | 2004-06-09 | 83756.75 | 83756.75 | [8 empty] | 0
| 7 | Relocate A/V & Fibre optic conduits | 9051 | 6859686.73 | 9051 |  | Comp | 7 | 2004-07-12 | 151546.89 | 151546.89 | [8 empty] | 0
| 8 | CR MEP -5 | 41247 | 6900933.73 | 41247 |  | Comp | 8 | 2004-08-11 | 173291.02 | 173291.02 | [8 empty] | 0
| 9 | MEP-11 Bereakers at Elevators | 15057 | 6915990.73 | 15057 |  | Comp | 9 | 2004-09-13 | 578169.67 | 578169.67 | [8 empty] | 0
| 10 | MEP-14 No n-West Area changes | 11004 | 6926994.73 | 11004 |  | Comp | 10 | 2004-10-13 | 529552.04 | 529552.04 | [8 empty] | 0
| 11 | Broad band cable system | 659007 | 7586001.73 | 659007 |  | Comp | 11 | 2004-11-12 | 249712.06 | 249712.06 | [8 empty] | 0
| 12 | Over for elevated slabs | 25483 | 7611484.73 | 25483 |  | Comp | 12 | 2004-12-06 | 320358.85 | 320358.85 | [8 empty] | 0
| 13 | MEP-9 | 198549 | 7810033.73 | 198549 |  | Comp | 13 | 2005-01-12 | 832680.51 | 832680.51 | [8 empty] | 0
| 14 | TV A/V and video changes | 167443.43 | 7977477.16 | 0 | 167443.43 | Comp | 14 | 2005-02-07 | 322682.51 | 322682.51 | [8 empty] | 0
| 15 | MEP-7 Fire alarm changes | 112767 | 8090244.16 | 112767 |  | Comp | 15 | 2005-03-08 | 719363.75 | 719363.75
| 16 | 36 S-1 lights at vomitories | 23130 | 8113374.16 | 23130 |  | Comp | 16 | 2005-04-06 | 105035.8 | 105035.8
| 17 | Floor trench duct | 31500 | 8144874.16 | 31500 |  | Comp | 17 | 2005-05-10 | 72910.6 | 72910.6
| 18 | Replace MC cable on lower concourse | 19254 | 8164128.16 | 19254 |  | Comp | 18 | 2005-06-08 | 461659.72 | 461659.72
| 19 | Basket ball court feeders | 9395 | 8173523.16 | 9395 |  | Comp | 19 | 2005-07-07 | 701692.94 | 522069.59 |  |  | 179623.35 | [5 empty] | 179623.35
| 20 | West space fit out | 392789 | 8566312.16 | 0 | 392789 | Comp | 20 | 2005-08-09 | 806599.81 | 610205.31 |  |  |  |  | 196394.5 |  |  |  | 196394.5
| 21 | West space fit out event level | 66610 | 8632922.16 | 66610 |  | Comp | 21 | 2005-09-08 | 308570.92 | 308570.92 | [8 empty] | 0
| 22 | Overtime 4/26/04 -6/14/04 | 11450 | 8644372.16 | 11450 |  | Comp | 22 | 2005-10-11 | 386046.41 | 128009.65 |  |  | 159366 |  | 58918.35 | 39752.41 |  |  | 258036.76
| 23 | Power for floor boxes in practice gym | 18516 | 8662888.16 | 18516 |  | Comp | 23 | 2005-11-08 | 254979.88 | 177688.47 |  |  |  | 25000 |  | 52291.41 |  |  | 77291.41
| 24 | Hall of Fame lighting | 13093.18 | 8675981.34 | 13093.18 |  | Comp | 24 | 2005-12-12 | 380856.61 | 341577.71 |  |  |  |  | 39278.9 |  |  |  | 39278.9
| 25 | Reroute temp feeders | 9953.15 | 8685934.49 | 9953.15 |  | Comp | 25 | 2006-01-09 | 217528.99 | 145751.06 |  |  | 68997.93 |  |  | 2780 |  |  | 71777.93
| 26 | Connect 15 KV feeders | 26264.69 | 8712199.18 | 26264.69 |  | Comp | 26 | 2006-02-07 | 301057.27 | 281417.82 |  |  |  |  | 19639.45 |  |  |  | 19639.45
| 27 | Catwalk rack changes | 36824.51 | 8749023.69 | 36824.51 |  | Comp | 27 | 2006-03-08 | 440190.81 | 246878.81 |  |  | 193312 | [5 empty] | 193312
| 28 | MEP -15 | 10114 | 8759137.69 | 10114 |  | Comp | 28 | 2006-04-10 | 222534.11 | 222534.11 | [8 empty] | 0
| 29 | MEP-25 | 40360 | 8799497.69 | 40360 |  | Comp | 29 | 2006-05-10 | 303328.84 | 5144.04 |  |  |  | 12872 | 92274.8 | 193038 |  |  | 298184.8
| 30 | Site 07 | 2447 | 8801944.69 | 2447 |  | Comp | 30 | 2006-06-07 | 57295.83 | 57295.83
| 31 | MEP-10 RFI 1041 | 11294 | 8813238.69 | 11294 |  | Comp | 31 | 2006-07-12 | 92900.74 | 92900.74
| 32 | MEP-13 | 2406 | 8815644.69 | 2406 |  | Comp | 32 | 2006-08-29 | 127603.4 | 127603.4
| 33 | AP-26 | 327286 | 9142930.69 | 150000 | 177286 | Comp | 33 | 2006-09-21 | 264313.74 | 264313.74
2006-01-17 | 34 | MEP-26 | 5317 | 9148247.69 | 5317 |  | Comp | 34 | 2006-10-09 | 296381.01 | 296381.01
2006-01-17 | 35 | G-5 Security gate changes | 9793 | 9158040.69 | 0 | 9793 | Comp | 35 | 2006-11-06 | 56963.62 | 56963.62
2006-01-17 | 36 | MEP-16 Hall of Fame | 15531 | 9173571.69 | 15531 |  | Comp | 36 | 2006-11-30 | 21345.26 | 21345.26
2006-01-17 | 37 | MEP-19 Exit sign changes | 3150 | 9176721.69 | 3150 |  | Comp | 37 | 2007-02-27 | 25636.6 | 25636.6
2006-01-17 | 38 | Increase Breaker Sizes | 8118.83 | 9184840.52 | 8118.83 |  | Comp | 38 | 2007-04-20 | 15175.3 | 15175.3
2006-01-17 | 39 | Cat-Walk rack changes | 11280.61 | 9196121.13 | 11280.61 |  | Comp | 39 | 2007-05-30 | 20626.87 | 20626.87
2006-01-17 | 40 | Trash compactor relocation | 5959 | 9202080.13 | 0 | 5959 | Comp | 40 | 2007-05-30 | 9032.64 | 9032.64
2006-01-17 | 41 | MEP-27 Misc. El;ect changes | 24832 | 9226912.13 | 0 | 24832 | Comp
2006-01-17 | 42 | Misc A/V changes | 46494 | 9273406.13 | 0 | 46494 | Comp
2006-05-01 | 43 | Connect kitchen equipment | 112872 | 9386278.13 | 0 | 112872 | Comp | [7 empty] | 112872 |  |  |  |  | 112872
2006-05-01 | 44 | Changes for elephant door | 79504.82 | 9465782.95 | 0 | 79504.82 | Comp | [9 empty] | 79504.82 |  |  | 79504.82
2006-05-01 | 45 | Relocate conduits in walls | 13869.18 | 9479652.13 | 13869.18 |  | Comp
2006-05-01 | 46 | Outlet changes for Arena Manager | 12539 | 9492191.13 |  | 12539 | Comp | [9 empty] | 12539
2006-05-01 | 47 | Soda Conduits | 25008 | 9517199.13 |  | 25008 | Comp | [7 empty] | 25008
2006-05-22 | 48 | AP-33,Ap-35 Mep- 30 | 34619.23 | 9551818.36 |  | 34619.23 | Comp
2006-05-22 | 49 | Conduit between telephone closets | 17819 | 9569637.36 |  |  | Comp
2006-05-26 | 50 | Structural for cat walk unistrut | 75023.82 | 9644661.18 |  |  | Comp
2006-05-26 | 51 | Additional groung grid | 16920.32 | 9661581.5 |  |  | Comp
2006-05-26 | 52 | Replace M-7 light fixtures | 8100 | 9669681.5 |  |  | Comp
2006-05-26 | 53 | Emerg Power for Fire/Smoke dampers | 43571.42 | 9713252.92 |  |  | Comp
2006-05-26 | 54 | Move roof exhaust fan starters | 29023 | 9742275.92 |  |  | Comp
2006-05-26 | 55 | Strut and light rack relocation | 23779.16 | 9766055.08 |  |  | Comp
2006-05-26 | 56 | Move boxes on concourse west wall | 5204.08 | 9771259.16 |  |  | Comp
2006-05-26 | 57 | Change lighting in west end | 13717 | 9784976.16 |  | 13717 | Comp
2006-05-26 | 58 | W. lobby video bd feeders | 17922 | 9802898.16 |  |  | Comp
2006-05-26 | 58 | Relocate AV cabinets | 8445.61 | 9811343.77 |  |  | Comp
2006-05-26 | 60 | Circuit for catwalk hoist | 2780 | 9814123.77 |  | 2780 | Comp
2006-05-26 | 61 | AP-36 | 584.73 | 9814708.5 |  |  | Comp
2006-05-26 | 62 | Aisle lighting , laundry | 17254 | 9831962.5 |  |  | Comp
2006-05-26 | 63 | Add outlets in Hall of Fame | 4999.78 | 9836962.28 |  |  | Comp
2006-05-26 | 64 | MEP-10 power at turnstiles | 11004 | 9847966.28 |  |  | Comp
2006-05-26 | 65 | Catwalk gutter changes | 4567.2 | 9852533.48 |  |  | Comp
2006-05-26 | 66 | Boiler breaker changes | 2322.4 | 9854855.88 |  |  | Comp
2006-05-26 | 67 | Shaft slab conduit | 13560 | 9868415.88 |  |  | Comp
2006-05-26 | 68 | Weather proof boxes for TV power | 7198 | 9875613.88 |  |  | Comp
2006-05-26 | 69 | Lights in corner and coaches stairs | 15324 | 9890937.88 |  |  | Comp
2006-05-26 | 70 | Overtime 9/19 - 11/28/05 | 58523 | 9949460.88 |  |  | Comp
2006-05-26 | 71 | Extre power for ribbon board | 193312 | 10142772.88 |  | 193312 | Comp
2006-05-26 | 72 | Conduit for wireless comm system | 56436 | 10199208.88 |  |  | Comp
2006-05-26 | 73 | Modify practice court light fixtures | 9477 | 10208685.88 |  |  | Comp
2006-05-26 | 74 | Credit for connection of kit equip. | -100000 | 10108685.88 |  | -100000 | Comp
2006-05-26 | 75 | Add transformers and dist per Bulletin 17 | 103583 | 10212268.88 |  |  | Comp
| 76 | VFD Line/Load Conduit | 8700 | 10220968.88 |  |  | Comp
| 77 | Shunt trips for concession hoods | 22350 | 10243318.88 |  |  | Comp
| 78 | Relocation at Control Room | 12482.65 | 10255801.53 |  |  | Comp
| 79 | Changes at Hot Tub | 15273.87 | 10271075.4 |  |  | Comp
| 80 | Panel for the elevators | 8710 | 10279785.4 |  |  | Comp
| 81 | Bollord fixtures - West plaza | 27874 | 10307659.4 |  |  | Comp
| 82 | Bulletin 3 & 5 | 41247.06 | 10348906.46 |  |  | Comp
| 83 | Additional T&M | 28709.7 | 10377616.16 |  |  | Comp
| 84 | Misc. T&M thru 6/15/06 | 39844.29 | 10417460.45 |  |  | Comp
| 85 | MEP 38 | 45789.71 | 10463250.16 |  |  | Comp
| 86 | Misc. T&M thru 7/31/06 | 41093.73 | 10504343.89 |  |  | Comp
| 87 | Elevator pit conections | 48582.2 | 10552926.09 |  |  | Comp
| 88 | T&M through August | 26200.99 | 10579127.08 |  |  | Comp
| 89 | Team Store | 83875 | 10663002.08 |  |  | Comp
| 90 | Misc. | 25413.45 | 10688415.53 |  |  | Comp
| 91 | Rough-in for coffee bar | 4932 | 10693347.53 |  |  | Comp
| 92 | Donor Suite Modification | 1003 | 10694350.53 |  |  | Comp
| 93 | Misc. repairs | 11995.13 | 10706345.66 |  |  | Comp
| 94 | Relocate fan in Quad B | 7284 | 10713629.66 |  |  | Comp
2007-02-20 | 95 | Team Store | -18782.18 | 10694847.48 |  |  | Comp
2007-02-20 | 96 | Halo Aisle Lighting | 43425 | 10738272.48 |  |  | Comp
2007-02-20 | 97 | Add. Parking Lot Lighting | 6969.87 | 10745242.35 |  |  | Comp
2007-03-21 | 98 | AHU 101-104 In-Line pump | 15974 | 10761216.35 |  |  | Comp
Total |  |  | 4080576.35 | 10761216.35 | 9562267.87 | 1198948.48 | 61.08% |  |  | 10761216.62 | 9427677.52 | 0 | 0 | 601299.28 | 175752 | 406506 | 379905.64 | 0 | 0 | 1183557.28
Balance | [9 empty] | -0.27 | [10 empty] | -3750576.35
East Coast Glass 15 |  | Glass and Glazing | PO# 349687 | 1800319 | [16 empty] | 1890319 | 90000
| 1 | AP-11, AP-2, AP-15,AP-16 | 8946 | 1809265 | 8946 |  | Comp | 1 | 2004-12-06 | 51917.5 | 51917.5 | [8 empty] | 0
| 2 | Misc ext. window systems | 21987 | 1831252 | 21987 |  | Comp | 2 | 2005-04-06 | 647183.1 | 647183.1 | [8 empty] | 0
2006-04-03 | 3 | West space revisions | 174839 | 2006091 | 174839 |  | Comp | 3 | 2005-05-10 | 12003.49 | 12003.49 | [8 empty] | 0
2006-04-03 | 4 | Upgrade Hardware | 23746.38 | 2029837.38 | 23746.38 |  | Comp | 4 | 2005-06-08 | 66046.37 | 66046.37
2006-04-03 | 5 | AP-5,AP-27,Radiator covers | 80198.37 | 2110035.75 | 80198.37 |  | Comp | 5 | 2005-07-07 | 85918.23 | 85918.23
| 6 | Clerestory flashing | 6843.42 | 2116879.17 | 6843.42 |  | Comp | 6 | 2005-08-09 | 51957.16 | 51957.16
| 7 | AP-39, AP-40, etched glass | 40145.7 | 2157024.87 | 40145.7 |  | Comp | 7 | 2005-09-08 | 15347.25 | 15347.25
| 8 | Door, frame and 4 mirrors | 6250 | 2163274.87 | 6250 |  | Comp | 8 | 2005-11-08 | 190009.01 | 190009.01
[5 empty] | 0 |  |  | 9 | 2005-12-12 | 75607.18 | 75607.18
[8 empty] | 10 | 2006-01-09 | 65050.06 | 65050.06
[8 empty] | 11 | 2006-02-08 | 33677.5 | 33677.5
[8 empty] | 12 | 2006-03-08 | 155093.56 | 155093.56
[8 empty] | 13 | 2006-04-10 | 201521.73 | 201521.73
[8 empty] | 14 | 2006-05-10 | 208332.17 | 208332.17
[8 empty] | 15 | 2006-06-07 | 81346.48 | 81346.48
[8 empty] | 16 | 2006-07-12 | 39453.46 | 39453.46
[8 empty] | 17 | 2006-07-12 | 100844.06 | 100844.06
[8 empty] | 18 | 2006-10-09 | 29122.06 | 29122.06
[8 empty] | 19 | 2006-11-30 | 48825.91 | 48825.91
[8 empty] | 20 | 2007-04-09 | 4018.59 | 4018.59
Total |  |  | 362955.87 | 2163274.87 | 2163274.87 |  | 20.16% |  |  | 2163274.87 | 2163274.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance | [9 empty] | 0 | [10 empty] | -272955.87
Piedmont Plaster 16 |  | Gypsum board | PO# 363670 | 2990630 | [16 empty] | 3160630 | 170000
| 1 | Revisions to west wall | 35912 | 3026542 | 35912 |  | Comp | 1 | 2004-07-12 | 28215 | 28215 | [8 empty] | 0
| 2 | AP -2 | 27384.4 | 3053926.4 | 27384.4 |  | Comp | 2 | 2004-08-11 | 29183.52 | 29183.52 | [8 empty] | 0
| 3 | AP-5 | 66533.75 | 3120460.15 | 66533.75 |  | Comp | 3 | 2004-09-13 | 129727.73 | 129727.73 | [8 empty] | 0
| 4 | Joists for deck lids | 47860 | 3168320.15 | 47860 |  | Comp | 4 | 2004-10-13 | 13879.5 | 13879.5 | [8 empty] | 0
| 5 | AP-11 | 40060.1 | 3208380.25 | 40060.1 |  | Comp | 5 | 2004-11-12 | 33582.5 | 33582.5 | [8 empty] | 0
| 6 | West space | 649148.8 | 3857529.05 | 0 | 649148.8 | Comp | 6 | 2004-12-06 | 40242 | 40242 | [8 empty] | 0
2006-03-07 | 7 | Up size steel framing etdc. | 36391 | 3893920.05 | 36391 |  | Comp | 7 | 2005-01-12 | 147389.49 | 147389.49 | [8 empty] | 0
2006-03-07 | 8 | Two hour lids UCC Quads B&C | 45818 | 3939738.05 | 45818 |  | Comp | 8 | 2005-02-07 | 61396.81 | 61396.81 | [8 empty] | 0
2006-03-07 | 9 | Additional cost for West spa ce | 67700 | 4007438.05 | 0 | 67700 | Comp | 9 | 2005-03-08 | 132317.9 | 132317.9 | [8 empty] | 0
2006-03-07 | 10 | AP 28 ceiling changes | 49898 | 4057336.05 | 49898 |  | Comp | 10 | 2005-04-06 | 141673.29 | 141673.29 | [8 empty] | 0
2006-03-07 | 11 | Walls between metal roof decks UCC | 29850 | 4087186.05 | 29850 |  | Comp | 11 | 2005-05-10 | 115794.42 | 115794.42 | [8 empty] | 0
2006-03-07 | 12 | Fir out 4 interior conc walls | 22194 | 4109380.05 | 22194 |  | Comp | 12 | 2005-06-08 | 276043.16 | 276043.16 | [8 empty] | 0
2006-03-07 | 13 | Fir out stucco at North Elevation | 31766 | 4141146.05 | 31766 |  | Comp | 13 | 2005-07-07 | 316477.63 | 316477.63 | [8 empty] | 0
2006-04-03 | 14 | AP-10 | 35455 | 4176601.05 | 35455 |  | Comp | 14 | 2005-08-09 | 177400.76 | 177400.76 | [8 empty] | 0
2006-04-03 | 15 | AP-32,34 &35 | 16311 | 4192912.05 | 16311 |  | Comp | 15 | 2005-09-08 | 580648.03 | 357227.53 |  |  |  |  | 223420.5 |  |  |  | 223420.5
2006-04-03 | 16 | AP-38 halo changes | 22462 | 4215374.05 | 22462 |  | Comp | 16 | 2005-10-11 | 380253.34 | 158162.18 |  |  |  |  | 222091.16 |  |  |  | 222091.16
2006-04-17 | 17 | 2-hour wall in mech shafts | 32793 | 4248167.05 | 32793 |  | Comp | 17 | 2005-11-08 | 161494.24 | 161494.24 | [8 empty] | 0
2006-04-17 | 18 | T&M patch work | 31826 | 4279993.05 | 31826 |  | Comp | 18 | 2005-12-12 | 217440.16 | 191465.82 |  |  |  |  | 25974.34 |  |  |  | 25974.34
2006-04-17 | 19 | Extencd walls at main elect room | 12155.61 | 4292148.66 | 12155.61 |  | Comp | 19 | 2006-01-09 | 327597.83 | 206972.22 |  |  |  |  | 120625.61 |  |  |  | 120625.61
2006-04-17 | 20 | AP-21 Misc changes | 3085 | 4295233.66 | 0 | 3085 | Comp | 20 | 2006-02-08 | 329531.57 | 329531.57 | [8 empty] | 0
2006-04-17 | 21 | Misc changes per AP-27 | -2308 | 4292925.66 | -2308 |  | Comp | 21 | 2006-03-08 | 232163.74 | 232163.74 | [8 empty] | 0
2006-04-17 | 22 | Acoustic ceiling changes AP-39 | 5305 | 4298230.66 | 5305 |  | Comp | 22 | 2006-04-10 | 242340.52 | 166574.26 |  |  |  |  | 75766.26 |  |  |  | 75766.26
2006-04-17 | 23 | Acoustic ceiling changes AP-40 | 8768 | 4306998.66 | 8768 |  | Comp | 23 | 2006-05-10 | 155114.41 | 43473.48 |  |  |  |  | 111640.93 |  |  |  | 111640.93
2006-04-17 | 24 | Rework soffits UCCN&S | 13132 | 4320130.66 | 13132 |  | Comp | 24 | 2006-06-07 | 141975.12 | 141975.12 | [8 empty] | 0
2006-04-19 | 25 | Extend horizontal shafts | 89777 | 4409907.66 | 89777 |  | Comp | 25 | 2006-07-12 | 78485.4 | 78485.4
2006-05-15 | 26 | Bulkheads at UCC toilet rooms | 15994 | 4425901.66 | 15994 |  | Comp | 26 | 2006-08-14 | 23468.83 | 23468.83
2006-05-22 | 27 | West End Changes | 59584.9 | 4485486.56 | 0 | 59584.9 | Comp | 27 | 2006-09-21 | 17861.71 | 17861.71
2006-05-22 | 28 | Misc framing and black cloth | 15528 | 4501014.56 | 15528 |  | Comp | 28 | 2006-10-09 | 40183.02 | 40183.02
2006-05-22 | 29 | Pipe bridge to power plant | 6090 | 4507104.56 | 6090 |  | Comp | 29 | 2006-11-06 | 121640.83 | 121640.83
2006-05-22 | 30 | Engineering V soffits & bulkheads | 5831 | 4512935.56 | 5831 |  | Comp | 30 | 2006-11-30 | 45000 | 45000
2006-05-22 | 31 | Revise ceiling types | 3133.9 | 4516069.46 | 3133.9 |  | Comp | 31 | 2007-02-28 | 26701.55 | 26701.55
2006-05-22 | 32 | Rated walls and spacers | 33539.46 | 4549608.92 | 33539.46 |  | Comp
2006-05-22 | 33 | Tectum panels in womens court | 27353 | 4576961.92 | 27353 |  | Comp
2006-07-05 | 34 | 2 hour lids for Elevator shafts | 26954 | 4603915.92 | 26954 |  | Comp
2006-07-05 | 35 | T&M 3/24/06-4/5/06 | 14250.43 | 4618166.35 | 14250.43 |  | Comp
| 36 | Paintings & Wallcovering- AP36 | 9015.8 | 4627182.15 | 9015.8 |  | Comp
| 37 | AP 26 Security Door Hardware | 5980 | 4633162.15 | 5980 |  | Comp
| 38 | Add reveals UCC-Quad B&C | 17018.1 | 4650180.25 | 17018.1 |  | Comp
| 39 | T&M Tickets through 5/12/06 | 24767.97 | 4674948.22 | 24767.97 |  | Comp
| 40 | Repair,rework, as of 6/2/06 | 41879.81 | 4716828.03 | 41879.81 |  | Comp
| 41 | Provide & install mirrors | 10322.4 | 4727150.43 | 10322.4 |  | Comp
| 42 | ACT repairs through 7/19/06 | 33828.49 | 4760978.92 | 33828.49 |  | Comp
| 43 | Work in Academic Center | 15356.8 | 4776335.72 | 15356.8 |  | Comp
| 44 | Athletic Dining Room door | 1855 | 4778190.72 | 1855 |  | Comp
| 45 | Add 1 layer of drywall Quad A | 6692.92 | 4784883.64 | 6692.92 |  | Comp
| 46 | Team Store drywall | 42500 | 4827383.64 | 42500 |  | Comp
| 47 | Chng wall type from S1-S to S2-S | -35000 | 4792383.64 | -35000 |  | Comp
| 48 | Deduct for deleted panels | -29585 | 4762798.64 | -29585 |  | Comp
| 49 | Add blocking for TV's | 725.41 | 4763524.05 | 725.41 |  | Comp
| 50 | Team Store, toilet partitions | 1699.96 | 4765224.01 | 1699.96 |  | Comp
Total |  |  | 1774594.01 | 4765224.01 | 3985705.31 | 779518.7 | 59.34% |  |  | 4765224.01 | 3985705.21 | 0 | 0 | 0 | 0 | 779518.8 | 0 | 0 | 0 | 779518.8
Balance | [9 empty] | 0 | [10 empty] | -1604594.01
James River Iron 17 |  | Misc. Metals | PO#354389 | 1814738 | [16 empty] | 1904738 | 90000
| 1 | GSP-3 & 4 and cont. angle | 36349 | 1851087 | 36349 |  | Comp | 1 | 2004-07-19 | 10315.1 | 10315.1 | [8 empty] | 0
| 2 | Install shelf angles | 49697 | 1900784 | 49697 |  | Comp | 2 | 2004-09-13 | 33056.92 | 33056.92 | [8 empty] | 0
| 3 | PCO 189,190,251,253,257,258 | 39344 | 1940128 | 39344 |  | Comp | 3 | 2004-11-12 | 108611.96 | 108611.96 | [8 empty] | 0
| 4 | PCO 254,259,272 | 44210 | 1984338 | 44210 |  | Comp | 4 | 2004-12-06 | 39152.44 | 39152.44 | [8 empty] | 0
| 5 | PCO 188,260,261 | 24090 | 2008428 | 24090 |  | Comp | 5 | 2005-01-12 | 14545.7 | 14545.7 | [8 empty] | 0
| 6 | PCO 252,271 | 48406 | 2056834 | 48406 |  | Comp | 6 | 2005-02-07 | 72020.91 | 72020.91 | [8 empty] | 0
| 7 | PCO 256, 273 | 37041 | 2093875 | 37041 |  | Comp | 7 | 2005-03-08 | 24234.79 | 24234.79
| 8 | Angle at roof gutter | 96111.25 | 2189986.25 | 96111.25 |  | Comp | 8 | 2005-04-06 | 20049.21 | 20049.21
| 9 | Curtain wall support steel | 28403.2 | 2218389.45 | 28403.2 |  | Comp | 9 | 2005-05-10 | 26703.28 | 26703.28
| 10 | RFI 947&1005 &ASP 18&19 | 21444 | 2239833.45 | 21444 |  | Comp | 10 | 2005-06-08 | 113471.23 | 113471.23
| 11 | PCO 401,427 &483 | 19180 | 2259013.45 | 19180 |  | Comp | 11 | 2005-07-07 | 172572.85 | 172572.85
| 12 | Misc Steel | 26337 | 2285350.45 | 12852 | 13485 | Comp | 12 | 2005-08-09 | 81491.68 | 81491.68
| 13 | Tube steel on HH line | 36682 | 2322032.45 | 36682 |  | Comp | 13 | 2005-09-08 | 21936.55 | 21936.55
2005-12-12 | 14 | Elephant door steel | 54687 | 2376719.45 | 0 | 54687 | Comp | 14 | 2005-10-11 | 169287.88 | 169287.88 | [8 empty] | 0
2007-01-24 | 15 | Misc. Metal Changes | 45699 | 2422418.45 |  |  | Comp | 15 | 2005-11-08 | 157414.24 | 157414.24
2007-01-24 | 16 | Add Access Ladders | 45658 | 2468076.45 |  |  | Comp | 16 | 2005-12-12 | 92838.04 | 92838.04
2007-01-24 | 17 | COR #53, COR #54 | 44442 | 2512518.45 |  |  | Comp | 17 | 2006-01-09 | 103787.13 | 90302.13 | [7 empty] | 13485 | 13485
2007-01-24 | 18 | Misc. T&M | 44094 | 2556612.45 |  |  | Comp | 18 | 2006-02-08 | 71281.11 | 71281.11 | [8 empty] | 0
2007-01-26 | 19 | Misc. T&M | 45933 | 2602545.45 |  |  | Comp | 19 | 2006-03-08 | 105250.22 | 105250.22 | [8 empty] | 0
2007-01-26 | 20 | Knockout panel - Practice | 18338 | 2620883.45 |  |  | Comp | 20 | 2006-04-10 | 115564.65 | 115564.65 | [8 empty] | 0
2007-01-26 | 21 | Misc. T&M | 48961 | 2669844.45 |  |  | Comp | 21 | 2006-05-10 | 224338.27 | 172385.62 | [6 empty] | 51952.65 |  | 51952.65
2007-01-26 | 22 | Deductive | -266692 | 2403152.45 |  |  | Comp | 22 | 2006-06-07 | 136659.78 | 136659.78
2007-01-26 | 23 | Misc. T&M | 31308 | 2434460.45 |  |  | Comp | 23 | 2006-08-29 | 62756.71 | 62756.71
| 24 | COR Adj. | 4043 | 2438503.45 |  |  | Comp | 24 | 2006-09-08 | 203467.44 | 203467.44
2007-03-15 | 25 | Misc. metal work | 49706 | 2488209.45 |  |  | Comp | 25 | 2007-01-30 | 192790.86 | 192790.86
2007-03-15 | 26 | Misc. metal work | 45304 | 2533513.45 |  |  | Comp | 26 | 2007-04-09 | 250584.51 | 250584.51
2007-03-15 | 27 | Misc. metal work | 47090 | 2580603.45 |  |  | Comp | 27 | 2007-04-12 | 14736 | 14736
2007-03-15 | 28 | Misc. metal work | 47623 | 2628226.45 |  |  | Comp
2007-05-23 | 29 | Additional Rails | 10693 | 2638919.45 |  |  | Comp
Total |  |  | 824181.45 | 2638919.45 | 2570747.45 | 68172 | 45.42% |  |  | 2638919.46 | 1911903 | 0 | 0 | 0 | 0 | 0 | 0 | 51952.65 | 13485 | 65437.65
Balance | [9 empty] | -0.01 | [10 empty] | -734181.45
STOVALL Engr. 18 |  | Metal Panels and Louvers | PO# 365843 | 1448751 | [16 empty] | 1518751 | 70000
| 1 | MWP brackets and gutter clips | 16106 | 1464857 | 16106 |  | comp | 1 | 2004-07-12 | 28937 | 28937 | [8 empty] | 0
| 2 | Overtime for monitor | 1916 | 1466773 | 1916 |  | comp | 2 | 2004-07-12 | 10640 | 10640 | [8 empty] | 0
|  | Charge to 249331 |  | 1466773 | -128000 | 128000 |  | 3 | 2005-01-12 | 266254.84 | 266254.84 | [8 empty] | 0
| 3 | Louver and MWP modifications | 31917 | 1498690 | 31917 |  | Comp | 4 | 2005-02-07 | 143800.64 | 143800.64 | [8 empty] | 0
| 4 | Quad C event level louver replace | 9100 | 1507790 | 9100 |  | Comp | 5 | 2005-03-08 | 191878.63 | 191878.63
| 5 | Metal canopy at SMG office | 17920 | 1525710 | 17920 |  | Comp | 6 | 2005-04-06 | 118674 | 118674
[8 empty] | 7 | 2005-05-10 | 131468.12 | 131468.12
[8 empty] | 8 | 2005-06-08 | 97480.59 | 97480.59
[8 empty] | 9 | 2005-07-07 | 111672.5 | 0 |  | 111672.5 | [6 empty] | 111672.5
[8 empty] | 10 | 2005-08-09 | 54427.4 | 38099.9 |  | 16327.5 | [6 empty] | 16327.5
[8 empty] | 11 | 2005-09-08 | 92715.24 | 92715.24
[8 empty] | 12 | 2005-10-11 | 26136.88 | 26136.88
[8 empty] | 13 | 2005-11-08 | 12592.25 | 12592.25
[8 empty] | 14 | 2004-12-12 | 32361.75 | 32361.75
[8 empty] | 15 | 2006-01-09 | 22807.12 | 22807.12
[8 empty] | 16 | 2006-02-08 | 20809.75 | 20809.75
[8 empty] | 17 | 2006-03-08 | 11307.38 | 11307.38
[8 empty] | 18 | 2006-04-10 | 17774.02 | 17774.02
[8 empty] | 19 | 2006-05-10 | 3040 | 3040
[8 empty] | 20 | 2006-06-07 | 14727.38 | 14727.38
[8 empty] | 21 | 2006-09-21 | 6051.5 | 6051.5
[8 empty] | 22 | 2006-09-21 | 12093.5 | 12093.5
[8 empty] | 23 | 2006-09-21 | 21774 | 21774
[8 empty] | 24 | 2006-11-30 | 38142.75 | 38142.75
[8 empty] | 25 | 2007-01-08 | 38142.75 | 38142.75
Total |  |  | 76959 | 1525710 | 1397710 | 128000 | 5.312% |  |  | 1525709.99 | 1397709.99 | 0 | 128000 | 0 | 0 | 0 | 0 | 0 | 0 | 128000
Balance | [9 empty] | 0.01 | [10 empty] | -6959
e TEC Fire Prot. 19 |  | Fire Protection Systems | PO#369335 | 587600 | [16 empty] | 616600 | 29000
| 1 | MEP-5 changes (3 toilet rooms) | 8790.75 | 596390.75 | 8790.75 |  | Comp | 1 | 2004-07-12 | 110984.7 | 110984.7 | [8 empty] | 0
| 2 | MEP-9 and MEP-14 | 11554.49 | 607945.24 | 11554.49 |  | Comp | 2 | 2004-08-11 | 1268.25 | 1268.25 | [8 empty] | 0
| 3 | Increase pipe sizes | 40264.27 | 648209.51 | 40264.27 |  | Comp | 3 | 2004-09-13 | 27469.25 | 27469.25 | [8 empty] | 0
| 4 | West end fire protection | 48394.34 | 696603.85 | 0.34 | 48394 | Comp | 4 | 2004-10-13 | 7381.5 | 7381.5 | [8 empty] | 0
2006-02-24 | 5 | Flex heads | 6665.4 | 703269.25 | 6665.4 |  | Comp | 5 | 2004-11-12 | 12305.59 | 12305.59 | [8 empty] | 0
2006-02-24 | 6 | Elephant door | 10431.64 | 713700.89 | 0 | 10431.64 | Comp | 6 | 2004-12-06 | 22429.5 | 22429.5 | [8 empty] | 0
2006-02-24 | 7 | Pipe for hose cabinet Quad B lower | 4611.5 | 718312.39 | 4611.5 |  | Comp | 7 | 2005-01-12 | 17576.39 | 17576.39 | [8 empty] | 0
2006-02-24 | 8 | 4 preaction panels | 6919.15 | 725231.54 | 6919.15 |  | Comp | 8 | 2005-02-07 | 53337.32 | 53337.32 | [8 empty] | 0
2006-05-15 | 9 | Hall of fame changes | 18779.2 | 744010.74 | 16092.58 | 2686.62 | Comp | 9 | 2005-03-08 | 40538.41 | 40538.41 | [8 empty] | 0
2006-06-09 | 10 | Replace broken pipe | 3217.7 | 747228.44 | 3217.7 |  | Comp | 10 | 2005-04-06 | 6702.15 | 6702.15 | [8 empty] | 0
| 11 | MEP 9 & 14 | 13462.76 | 760691.2 | 13462.76 |  | Comp | 11 | 2005-05-10 | 50821.53 | 50821.53 | [8 empty] | 0
| 12 | Add 6 sprinkler heads | 14237.09 | 774928.29 | 14237.09 |  | Comp | 12 | 2005-06-08 | 41618.82 | 41618.82 | [8 empty] | 0
| 13 | Relocate sprinkler heads | 4349.52 | 779277.81 | 4349.52 |  | Comp | 13 | 2005-07-07 | 41582.34 | 41582.34 | [8 empty] | 0
| 14 | T&M tickets through 7-15-06 | 17771.03 | 797048.84 | 17771.03 |  | Comp | 14 | 2005-08-09 | 26600 | 26600 | [8 empty] | 0
| 15 | T&M tickets through 8-30-06 | 9617 | 806665.84 | 9617 |  | Comp | 15 | 2005-09-08 | 40902.48 | 40902.48 | [8 empty] | 0
2007-02-20 | 16 | T&M Tickets | 11616.87 | 818282.71 | 11616.87 |  | Comp | 16 | 2005-10-11 | 84365.37 | 37637.97 |  |  |  |  | 36295.76 | 10431.64 |  |  | 46727.4
[8 empty] | 17 | 2005-11-08 | 14119.06 | 9279.63 |  |  |  |  | 4839.43 |  |  |  | 4839.43
[8 empty] | 18 | 2005-12-12 | 14485.6 | 14485.6 | [8 empty] | 0
[8 empty] | 19 | 2006-01-09 | 14826.59 | 14826.59 | [8 empty] | 0
[8 empty] | 20 | 2006-02-08 | 9730.38 | 9730.38 | [8 empty] | 0
[8 empty] | 21 | 2006-03-08 | 18650.98 | 13811.55 |  |  |  |  | 4839.43 |  |  |  | 4839.43
[8 empty] | 22 | 2006-04-10 | 19474.19 | 19474.19 | [8 empty] | 0
[8 empty] | 23 | 2006-05-10 | 17840.24 | 15154.24 |  |  |  |  | 2686 |  |  |  | 2686
[8 empty] | 24 | 2006-06-07 | 28214.51 | 26762.68 |  |  |  |  | 1451.83 |  |  |  | 1451.83
[8 empty] | 25 | 2006-07-12 | 12372.56 | 11404.67 |  |  |  |  | 967.89 |  |  |  | 967.89
[8 empty] | 26 | 2006-08-14 | 21917.3 | 21917.3
[8 empty] | 27 | 2006-09-21 | 8342.9 | 8342.9
[8 empty] | 28 | 2006-10-09 | 6112.63 | 6112.63
[8 empty] | 29 | 2006-10-09 | 20315 | 20315
[8 empty] | 30 | 2007-01-25 | 25997.15 | 25997.15
Total |  |  | 230682.71 | 818282.71 | 756770.45 | 61512.26 | 39.26% |  |  | 818282.69 | 674085.73 | 0 | 0 | 0 | 0 | 51080.34 | 10431.64 | 0 | 0 | 51080.34
Balance | [9 empty] | 0.02 | [10 empty] | -201682.71
Augusta Steel Co. 20 |  | HM Doors and Frames | PO#368981 | 325506 | [16 empty] | 341506 | 16000
2006-06-12 | 1 | AP-26 | 37439.85 | 362945.85 | 37439.85 |  | comp | 1 | 2004-08-11 | 77252.01 | 77252.01 | [8 empty] | 0
2006-06-12 | 2 | AP-5 and AP-11 | 10120 | 373065.85 | 10120 |  | comp | 2 | 2004-09-13 | 65515.33 | 65515.33 | [8 empty] | 0
2006-06-15 | 3 | West Space AP-10 | 73676 | 446741.85 | 0 | 73676 | Comp | 3 | 2005-06-08 | 61910.59 | 61910.59 | [8 empty] | 0
2006-06-15 | 4 | AP-13 and AP-30 | 19984.95 | 466726.8 | 19984.95 |  | Comp | 4 | 2005-09-08 | 22409.64 | 22409.64 | [8 empty] | 0
2006-06-15 | 5 | AP 15, 21,25,27,34 and 36 | 23367 | 490093.8 | 23367 |  | Comp | 5 | 2006-05-01 | 103864.79 | 103864.79 | [8 empty] | 0
2007-03-12 | 6 | Misc. repairs and additions | 18410 | 508503.8 | 18410 |  | comp | 6 | 2006-05-16 | 115825.07 | 42149.07 |  |  |  |  | 73676 |  |  |  | 73676
[8 empty] | 7 | 2007-01-26 | 36301.19 | 36301.19
[8 empty] | 8 | 2007-01-26 | 12712.59 | 12712.59
[8 empty] | 9 | 2007-02-21 | 12712.6 | [9 empty] | 0
Total |  |  | 182997.8 | 508503.8 | 434827.8 | 73676 | 56.22% |  |  | 508503.81 | 422115.21 | 0 | 0 | 0 | 0 | 73676 | 0 | 0 | 0 | 73676
Balance | [9 empty] | -0.01 | [10 empty] | -166997.8
Alexander Water 21 |  | Waterproofing | PO#376973 | 192000 | [16 empty] | 202000 | 10000
| 1 | Additional waterproofiing | 30107 | 222107 | 30107 |  | Comp | 1 | 2004-08-11 | 24348.5 | 24348.5 | [8 empty] | 0
| 2 | Waterproofing at elevator pits | 2279 | 224386 | 2279 |  | Comp | 2 | 2004-11-12 | 68319.25 | 68319.25 | [8 empty] | 0
[5 empty] | 0 |  |  | 3 | 2005-01-12 | 12531.41 | 12531.41 | [8 empty] | 0
|  |  |  | 0 | 0 |  |  | 4 | 2005-02-07 | 6028.74 | 6028.74 | [8 empty] | 0
[5 empty] | 0 |  |  | 5 | 2005-05-10 | 16088.25 | 16088.25
[5 empty] | 0 |  |  | 6 | 2005-06-08 | 20800.25 | 20800.25
[5 empty] | 0 |  |  | 7 | 2005-07-07 | 17931.25 | 17931.25
[5 empty] | 0 |  |  | 8 | 2005-09-08 | 11067.5 | 11067.5
[5 empty] | 0 |  |  | 9 | 2005-11-08 | 14345 | 14345
[5 empty] | 0 |  |  | 10 | 2005-12-12 | 5631.6 | 5631.6
[8 empty] | 11 | 2006-01-09 | 13909.9 | 13909.9
[8 empty] | 12 | 2006-09-08 | 2165.05 | 2165.05
[8 empty] | 13 | 2006-09-08 | 11219.3 | 11219.3
Total |  |  | 32386 | 224386 | 224386 |  | 16.87% |  |  | 224386 | 224386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance | [9 empty] | 0 | [10 empty] | -22386
K Plus Services 22 |  | Joint Sealants | PO# 452498 | 188063 | [16 empty] | 198063 | 10000
2006-06-21 | 1 | Calk saw cut joints in Park Gar. | 16073.4 | 204136.4 | 16073.4 |  | comp | 1 | 2005-08-09 | 8444.64 | 8444.64 | [8 empty] | 0
2006-06-21 | 2 | Caulk weld plates in garage | 8500 | 212636.4 | 8500 |  | comp | 2 | 2005-08-09 | 12036.74 | 12036.74 | [8 empty] | 0
2006-06-21 | 3 | Temp waterproofing in bowl | 29000 | 241636.4 | 29000 |  | comp | 3 | 2005-09-12 | 36334.72 | 36334.72 | [8 empty] | 0
2006-06-21 | 4 | Grind saw cut joints | 7188.5 | 248824.9 | 7188.5 |  | comp | 4 | 2005-11-08 | 10034.6 | 10034.6
2006-06-21 | 5 | Fill in plug holes | 1725 | 250549.9 | 1725 |  | comp | 5 | 2005-11-08 | 26604.77 | 26604.77
2006-06-21 | 6 | Caulk Bowl vomitories | 1537.5 | 252087.4 | 1537.5 |  | comp | 6 | 2005-12-12 | 24994.12 | 24994.12
2006-06-21 | 7 | T&M 1/12/06 --2/28/06 | 32568.75 | 284656.15 | 32568.75 |  | comp | 7 | 2006-01-09 | 22833.06 | 22833.06
2006-06-21 | 8 | T&M 3/2/06 -- 3/20/06 | 37023.75 | 321679.9 | 37023.75 |  | comp | 8 | 2006-02-08 | 21082.12 | 21082.12
| 9 | Misc. T&M | 14299.8 | 335979.7 | 14299.8 |  | comp | 9 | 2006-03-08 | 13757.28 | 13757.28
2007-01-24 | 10 | T&M thru 10-19-06 | 11144.28 | 347123.98 | 11144.28 |  | comp | 10 | 2006-04-10 | 17795.54 | 17795.54
[8 empty] | 11 | 2006-05-16 | 5787.4 | 5787.4
[8 empty] | 12 | 2006-05-16 | 93059.44 | 93059.44
[8 empty] | 13 | 2006-06-07 | 3643.25 | 3643.25
[8 empty] | 14 | 2006-07-12 | 3643.25 | 3643.25
[8 empty] | 15 | 2006-08-14 | 19127.88 | 19127.88
[8 empty] | 16 | 2006-11-06 | 19780.77 | 19780.77
[8 empty] | 17 | 2007-01-25 | 8164.4 | 8164.4
Total |  |  | 159060.98 | 347123.98 | 347123.98 |  | 84.58% |  |  | 347123.98 | 347123.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance | [9 empty] | 0 | [10 empty] | -149060.98
G.C. Zarnas & Co. 23 |  | Spray Applied Fireproofing | PO#466762 | 210097
| 1 | Lower concourse Quad A&B | 10000 | 220097 | 10000 |  | Comp | 1 | 2005-09-28 | 41665.86 | 41665.86 | [8 empty] | 0
| 2 | Fireproof additional beams | 14021.22 | 234118.22 | 14021.22 |  | Comp | 2 | 2005-09-28 | 66693.04 | 66693.04 | [8 empty] | 0
2006-03-20 | 3 | Additional fireproofing | 16574.3 | 250692.52 | 16574.3 |  | Comp | 3 | 2005-09-28 | 37746.35 | 37746.35 | [8 empty] | 0
2006-08-14 | 4 | Spray additional steel | 74024 | 324716.52 | 74024 |  | Comp | 4 | 2005-10-11 | 49306.9 | 49306.9
| 5 | Additional fireproofing | 9913 | 334629.52 | 9913 |  | Comp | 5 | 2006-02-08 | 22820.16 | 22820.16
| 6 | Deduct unused T&M | -3386.26 | 331243.26 | -3386.26 |  | Comp | 6 | 2006-03-08 | 15745.58 | 15745.58
[8 empty] | 7 | 2006-05-10 | 70322.8 | 70322.8
[8 empty] | 8 | 2007-01-26 | 963.06 | 963.06
[8 empty] | 9 | 2007-01-26 | 25979.51 | 25979.51
Total |  |  | 121146.26 | 331243.26 | 331243.26 |  | 57.66% |  |  | 331243.26 | 331243.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance | [6 empty] | 6/7/06% |  |  | 0 | [10 empty] | -331243.26
Faulconer Const. 24 |  | North Grounds Connector | PO#409769 | 4168370 | [16 empty] | 4378370 | 210000
2006-01-25 | 1 | Elect changes nd E&S work | 30668 | 4199038 | 30668 |  | Comp | 1 | 2005-05-10 | 114768.59 | 114768.59
2006-01-25 | 2 | Storm piping changes RFI NGC-2 | 48557 | 4247595 | 48557 |  | Comp | 2 | 2005-06-08 | 213688.79 | 213688.79
2006-01-25 | 3 | Storm water changes RFI 3,4 &10 | 46635 | 4294230 | 46635 |  | Comp | 3 | 2005-07-07 | 477473.55 | 477473.55
2006-01-25 | 4 | Landscaping per CR NGC-5 | 47558 | 4341788 | 47558 |  | Comp | 4 | 2005-08-09 | 581760.51 | 581760.51
2006-01-25 | 5 | Unsuitable soil near MSE wall | 49620 | 4391408 | 49620 |  | Comp | 5 | 2005-09-08 | 1151350.83 | 1151350.83
2006-01-25 | 6 | Project accelleration | 26596 | 4418004 | 26596 |  | Comp | 6 | 2005-10-11 | 258826.4 | 258826.4
2006-03-27 | 7 | Misc. Credits | -5943 | 4412061 | -5943 |  | Comp | 7 | 2005-11-08 | 479717.44 | 479717.44
| 8 | Credit unused units | -14500 | 4397561 | -14500 |  | Comp | 8 | 2005-12-12 | 764727.18 | 764727.18
[8 empty] | 9 | 2006-01-09 | 67410.01 | 67410.01
[8 empty] | 10 | 2006-02-08 | 67795.8 | 67795.8
[8 empty] | 11 | 2006-04-10 | 109906.8 | 109906.8
[8 empty] | 12 | 2006-11-06 | 110135.1 | 110135.1
Total |  |  | 229191 | 4397561 | 4397561 |  | 5.498% |  |  | 4397561 | 4397561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance | [9 empty] | 0 | [10 empty] | -19191
G.C.Zarnas & Co. 25 |  | Painting and Wall Covering | PO#467548 | 557913 | [16 empty] | 4378370 | 210000
| 1 | Garage expansion joints | 48840 | 606753 | 48840 |  | Comp | 1 | 2005-10-10 | 26650.97 | 26650.97
| 2 | Paint Halo etc. | 23102 | 629855 | 23102 |  | Comp | 2 | 2005-10-10 | 56836.64 | 56836.64
2006-04-11 | 3 | Paint east end of Halo | 12444.5 | 642299.5 | 12444.5 |  | Comp | 3 | 2005-10-10 | 20398.21 | 20398.21
2006-04-19 | 4 | Block filler on CMU walls | 84981 | 727280.5 | 84981 |  | Comp
2006-04-19 | 5 | AP-36,39,40 and elephant door | 23725 | 751005.5 | 23725 |  | Comp | 4 | 2005-12-12 | 39936.21 | 39936.21
2006-07-06 | 6 | Stained concrete | 7022.53 | 758028.03 | 7022.53 |  | Comp | 5 | 2005-12-12 | 30001.9 | 30001.9
| 7 | T&M Tickets thru 5/18/06 | 115795.63 | 873823.66 | 115795.63 |  | Comp | 6 | 2006-01-09 | 55864.74 | 55864.74
| 8 | Touch up paint | 62309.03 | 936132.69 | 62309.03 |  | Comp | 7 | 2006-02-08 | 44337.51 | 44337.51
| 9 | Touch up paint - Event level | 31458.87 | 967591.56 | 31458.87 |  | Comp | 8 | 2006-03-08 | 93318.04 | 93318.04
| 10 | Bond adjustment | 1267.43 | 968858.99 | 1267.43 |  | Comp | 9 | 2006-04-10 | 97423.83 | 97423.83
| 11 | Painting T&M | 813.16 | 969672.15 | 813.16 |  | Comp | 10 | 2006-05-10 | 144982.04 | 144982.04
[8 empty] | 11 | 2006-06-07 | 23941.45 | 23941.45
[8 empty] | 12 | 2006-08-14 | 197821.59 | 197821.59
[8 empty] | 13 | 2006-09-21 | 59193.58 | 59193.58
[8 empty] | 14 | 2007-01-08 | 25757.23 | 25757.23
[8 empty] | 15 | 2007-01-26 | 3952.4 | 3952.4
[8 empty] | 16 | 2007-01-26 | 49256.13 | 49256.13
Total |  |  | 411759.15 | 969672.15 | 969672.15 |  | 73.8% |  |  | 969672.47 | 969672.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance | [9 empty] | -0.32 | [10 empty] | 3408697.85
Creative Cabinet Sys 26 |  | Millwork | PO# 467975 | 1560245 | [16 empty] | 4378370 | 210000
| 1 | Value engineering | -147409 | 1412836 | -147409 |  | Comp | 1 | 2005-11-08 | 72553.4 | 72553.4
2006-03-08 | 2 | Add stainless steel to counters | 13402.16 | 1426238.16 | 13402.16 |  | Comp | 2 | 2006-01-09 | 362307.04 | 362307.04
2006-03-08 | 3 | Vanity women coaches | 2074.43 | 1428312.59 | 2074.43 |  | Comp | 3 | 2006-02-08 | 33135.21 | 33135.21
2006-05-01 | 4 | Stainless steel base | 17937.99 | 1446250.58 | 17937.99 |  | Comp | 4 | 2006-03-08 | 156102.1 | 156102.1
2006-06-14 | 5 | stain lockers | 11604.26 | 1457854.84 | 11604.26 |  | Comp | 5 | 2006-04-10 | 105099.05 | 105099.05
2006-08-21 | 6 | Stainless steel changes | 20105.01 | 1477959.85 | 20105.01 |  | Comp | 6 | 2006-05-10 | 442369.76 | 442369.76
| 7 | Bulletin 21 | 8825.25 | 1486785.1 | 8825.25 |  | Comp | 7 | 2006-06-07 | 59982.7 | 59982.7
| 8 | Misc. T&M | 21169.87 | 1507954.97 | 21169.87 |  | Comp | 8 | 7/1/2/06 | 126313.14 | 126313.14
| 9 | Team Store Millwork | 96622.95 | 1604577.92 | 96622.95 |  | Comp | 9 | 2006-08-14 | 19099.76 | 19099.76
| 10 | Team Store glass shelving | 4507.84 | 1609085.76 | 4507.84 |  | Comp | 10 | 2006-11-06 | 124569.61 | 124569.61
| 11 | Reinstall mirror in Suite 3C16 | 2603.6 | 1611689.36 | 2603.6 |  | Comp | 11 | 2007-01-26 | 69865.36 | 69865.36
[8 empty] | 12 | 2007-02-19 | 40292.23 | 40292.23
Total |  |  | 51444.36 | 1611689.36 | 1611689.36 |  | 3.297% |  |  | 1611689.36 | 1611689.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance | [9 empty] | 0 | [10 empty] | 2766680.64
David Allen Co. 27 |  | Ceramic Tile | PO# 455773 | 435711 | [16 empty] | 4378370 | 210000
2006-08-21 | 1 | VE and tile changes | 11055 | 446766 | 11055 |  | Comp | 1 | 2006-02-08 | 218381.77 | 218381.77
2006-08-21 | 2 | Add shower tile in1A18B | 3015 | 449781 | 3015 |  | Comp | 2 | 2006-03-08 | 52089.78 | 52089.78
| 3 | Tile materials for repair | 3770 | 453551 | 3770 |  | Comp | 3 | 2006-04-10 | 31939.49 | 31939.49
| 4 | Misc. T&M tickets | 6585 | 460136 |  |  | Comp | 4 | 2006-06-07 | 77125.74 | 77125.74
[8 empty] | 5 | 2006-11-06 | 47755.17 | 47755.17
[8 empty] | 6 | 2007-02-02 | 9837.25 | 9837.25
[8 empty] | 7 | 2007-02-02 | 18006.8 | 18006.8
[8 empty] | 8 | 2007-03-06 | 5000 | 5000
Total |  |  | 24425 | 460136 | 460136 |  | 5.606% |  |  | 460136 | 460136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance | [9 empty] | 0 | 920272 | [9 empty] | 3918234
Barranger |  | Toilet Partitions | PO# | 77410 | [16 empty] | 4378370 | 210000
| 1 |  | 500 | 77910 |  |  |  | 1 | 2006-04-12 | 81049 | 81049
| 2 |  | 3139 | 81049 |  |  |  | 2 | 2006-06-22 | 5473 | 5473
| 3 |  | 5473 | 86522 |  |  |  | 3 | 2206-06-01 | 493 | 493
| 4 |  | 493 | 87015 |  |  |  | 4 | 2006-10-25 | 887.4
[8 empty] | 5 | 2006-12-20 | 860.9
[9 empty] | 2006-09-07 | 444
[9 empty] | 2006-06-22 | 3378
Total |  |  | 9605 | 87015 | 87015 |  |  |  |  | 92585.3 |  | 0 | 0 | 0 | 0 | 0
Balance | [9 empty] | -5570.3 | 87015 | [9 empty] | 4291355
Color-Ad |  | Signage | PO# | 274372 | [16 empty] | 4378370 | 210000
| 1 |  | 0 |  |  |  |  | 1 | 2006-06-19 | 189639.81 | 189639.81
| 2 | [7 empty] | 2006-10-06 | 31620.55 | 31620.55
| 3 | Hanging banners | 9242.5 | 9245.5 |  |  |  |  | 2006-01-06 | 13032.67 | 13032.67
Total |  |  | 9242.5 | 283614.5 | 283614.5 |  |  |  |  | 234293.03 |  | 0 | 0 | 0 | 0 | 0
Balance | [9 empty] | 49321.47 | 234293.03 | [9 empty] | 4094755.5
Total |  |  | 36444481.11 | 84926741.44 | 108230081.54 | 13141141.01 |  |  |  | 121225209.8 | 97691181.29 | 138127.4 | 1319923 | 6853313.76 | 1211449.92 | 2182620.69 | 494560.28 | 51952.65 |  | 11863239.42 |  | 4904000
Total Including CO's |  |  | 36435238.61 | 121371222.55 | [5 empty] | 117856833.64
Total Balance | [9 empty] | 102261.9 | [10 empty] | -31244102.1
|  |  | check | 36444481.11 | [5 empty] | 117959095.54 |  | 119077234.79 | [9 empty] | 5200379.01
|  | CO's not including BMC | 18165718.89
Off Project costs |  |  |  | 13141141.01
Project Change orders |  |  |  | 23303340.1
Total Project costs |  |  |  | 108230081.54

## Sheet2
MULTIPURPOSE ARENA |  | 2026-07-28
Change Orders |  | Contractor payments |  |  | Charged to |  | HECO-8 | HECO-8
[5 empty] | other Projects |  | Budget | Contingency
BMC -01 | Phase 1 |  |  | PO# 163401
| Total | [5 empty] | 608767 | 0
CO # | Amount | Pay. Date | Pay. # | Amount
1 | 47000 | 2002-05-28 | 1 | 25000
2 | 27800 | 2002-08-06 | 2 | 100000
3 | 10461.66 | 2002-10-18 | 3 | 115000
|  | 2002-11-19 | 4 | 70000
|  | 2002-11-25 | 5 | 55000
|  | 2003-01-08 | 6 | 90000
|  | 2003-01-15 | 7 | 145000
|  | 2003-02-20 | 8 | 65000
|  | 2003-06-03 | 9 | 15000
|  | 2003-07-16 | 10 | 14028.66
Total | 85261.66 |  |  | 694028.66
Balance |  |  |  | -608767 |  |  | 523505.34
BMC -01 | Phase 2 |  |  | PO# 253722
| 362158 | [5 empty] | 362158 | 0
CO # | Amount | Pay. Date | Pay # | Amount
1 | 16164.58 | 2003-03-20 | 1 | 60000
|  | 2003-04-09 | 2 | 100000
|  | 2003-05-21 | 3 | 102000
|  | 2003-06-03 | 4 | 100158
|  | 2003-07-16 | 5 | 16164.58
Total | 378322.58 |  |  | 378322.58
Balance |  |  |  | 0 |  |  | -16164.58
BMC - 01 | Phase 3 |  |  | PO# 284782
| 6823226.44 | [5 empty] | 7547765 | 1300000
CO# | Amount | Pay Date | Pay # | Amount
1 | 5000 | 2003-08-01 | 1 | 262929.24
|  | 2003-08-11 | 2 | 220099.49
|  | 2003-09-02 | 3 | 170026.68
|  | 2003-10-01 | 4 | 190250.09
|  | 2003-11-12 | 5 | 195143.27
|  | 2003-12-02 | 6 | 198651.73
|  | 2004-01-14 | 7 | 191951.98
|  | 2004-02-09 | 8 | 229727.17 | 32684 | WO208818
Total | 6828226.44 |  |  | 1658779.65 | 32684
Balance |  |  |  | 5169446.79 |  |  | 719538.56
Faulconer - 02 Early Site Work |  |  |  | PO#269543
| 2059723 | [5 empty] | 2118723 | 59000
CO# | Amount | Pay Date | Pay # | Amount
1 | 30465 | 2003-05-14 | 1 | 140993.4
2 | 30816 | 2003-06-17 | 2 | 119659.91
3 | 36254 | 2003-07-16 | 3 | 310350.75
4 | 25119 | 2003-08-06 | 4 | 127498.65
5 | 25146 | 2003-09-09 | 5 | 159364.31
6 | 75525 | 2003-10-13 | 6 | 132163.89
7 | 120411 | 2003-11-24 | 7 | 391466.52
8 | 33600 | 2003-12-15 | 8 | 248910.26
9 | 13934 | 2004-01-19 | 9 | 171086.93
10 | 49441 | 2004-02-09 | 10 | 102492.85 | 43456 | WO208818
11 | -49164 | 2004-03-15 | 11 | 79682.45
|  | 2004-04-06 | 12 | 42560.85
Total | 2451270 |  |  | 2026230.77 | 43456
Balance |  |  |  | 425039.23 |  |  | -332547
Sumter Utilities -03 Dust Bank |  |  |  | PO# 290227
| 588000 | [5 empty] | 618000 | 30000
CO# | Amount | Pay Date | Pay # | Amount
|  | 2003-08-05 | 1 | 61807
|  | 2003-08-06 | 2 | 167646.5
|  | 2003-09-09 | 3 | 223290.38
|  | 2003-10-08 | 4 | 78557.7
Total | 588000 |  |  | 531301.58
Balance |  |  |  | 56698.42 |  |  | 30000
Cleveland Cem - 04 P. G. Foundation |  |  |  | PO# 275954
| 1598200 | [5 empty] | 1678200 | 80000
CO# | Amount | Pay Date | Pay # | Amount
1 | 291000 | 2003-08-06 | 1 | 283489.5
2 | 174919 | 2003-09-09 | 2 | 401849.52
3 | 45660 | 2003-10-05 | 3 | 228332.5
4 | 30140 | 2003-11-24 | 4 | 355100.5
|  | 2004-12-15 | 5 | 301791.25
|  | 2004-01-19 | 6 | 160331.5
|  | 2004-02-09 | 7 | 40850
|  | 2004-03-15 | 8 | 72010
|  | 2004-04-06 | 9 | 35625
Total | 2139919 |  |  | 1879379.77
Balance |  |  |  | 260539.23 |  |  | -461719
Faulconer -05 Arena Site Work |  |  |  | PO # 306970
| 8015000 | [5 empty] | 8415000 | 400000
CO# | Amount | Pay Date | Pay # | Amount
1 | 111773 | 2003-10-13 | 1 | 240730
2 | 31503 | 2003-10-08 | 2 | 600020
3 | 133462 | 2003-11-18 | 3 | 887490
4 | 449775 | 2003-12-15 | 4 | 585630.73
|  | 2004-01-19 | 5 | 175168.98
|  | 2004-02-09 | 6 | 65422.94
|  | 2004-03-15 | 7 | 235282.94
|  | 2004-04-06 | 8 | 336032.77
Total | 8741513 |  |  | 3125778.36
Balance |  |  |  | 5615734.64 |  |  | -326513
Shockey Precast 06 Structural Precast |  |  |  | PO # 317105
| 5927448 | [5 empty] | 6227448 | 300000
CO# | Amount | Pay Date | Pay # | Amount
|  | 2003-11-25 | 1 | 72359
|  | 2004-01-19 | 2 | 80463
|  |  | 3 | 19586
|  | 2004-03-15 | 4 | 34169
|  | 2004-04-06 | 5 | 101530
Total | 5927448 |  |  | 308107
Balance |  |  |  | 5619341 |  |  | 300000
Cleveland Cem -07 CIP Concrete |  |  |  | PO # 314843
| 10193300 | [5 empty] | 10693300 | 500000
CO# | Amount | Pay Date | Pay # | Amount
|  | 2003-11-25 | 1 | 108015
|  | 2003-12-15 | 2 | 348944.5
|  | 2004-01-19 | 3 | 333280.9
|  | 2004-02-09 | 4 | 854773.9
|  | 2004-03-15 | 5 | 877314.55
|  | 2004-04-06 | 6 | 1047713.2
Total | 10193300 |  |  | 3570042.05
Balance |  |  |  | 6623257.95 |  |  | 500000
Hirschfield Steel -08 Structural Steel |  |  |  | PO#321203
| 6695080 | [5 empty] | 6995080 | 300000
CO# | Amount | Pay Date | Pay # | Amount
1
2
Total | 6695080
Balance |  |  |  | 6695080 |  |  | 300000
Shockey Precast Group -09 Architectural Precast Conc. PO #
| 1318197 | [5 empty] | 1383197 | 65000
CO# | Amount | Pay Date | Pay # | Amount
1
2
Total | 1318197
Balance |  |  |  | 1318197 |  |  | 65000
Thyssen Krupp 10 -Elevators |  |  |  | PO#
| 599017 | [5 empty] | 628017 | 29000
CO# | Amount | Pay Date | Pay # | Amount
1
2
Total | 599017
Balance |  |  |  | 599017 |  |  | 29000
Bat Masonry 11 Masonry |  |  |  | PO#
| 4295000 | [5 empty] | 4495000 | 200000
CO# | Amount | Pay Date | Pay # | Amount
1
2
Total | 4295000
Balance |  |  |  | 4295000 |  |  | 200000
Roof Services Corp. 12 Roofing |  |  |  | PO#
| 1320760 | [5 empty] | 1386760 | 66000
CO# | Amount | Pay Date | Pay # | Amount
1
2
Total | 1320760
Balance |  |  |  | 1320760 |  |  | 66000
Colonial Mechanical 13 Mech and Plumb. |  |  |  | PO#343945
| 11210500 | [5 empty] | 11760500 | 550000
CO# | Amount | Pay Date | Pay # | Amount
|  | 2004-03-29 | 1 | 128250
|  | 2004-03-29 | 2 | 410454.15
|  | 2004-04-06 | 3 | 367445.75
Total | 11210500 |  |  | 906149.9
Balance |  |  |  | 10304350.1 |  |  | 550000
Design Electric 14 Electrical |  |  |  | PO#333364
| 6680640 | [5 empty] | 7010640 | 330000
CO# | Amount | Pay Date | Pay # | Amount
|  | 2004-02-09 | 1 | 206087.3
|  | 2004-02-09 | 2 | 115330
|  | 2004-03-15 | 3 | 146428.25
|  | 2004-04-06 | 4 | 225239.3
Total | 6680640 |  |  | 693084.85
Balance |  |  |  | 5987555.15 |  |  | 330000
East Coast Glass 15 Glass and Glazing |  |  |  | PO#
| 1800319 | [5 empty] | 1890319 | 90000
CO# | Amount | Pay Date | Pay # | Amount
1
2
Total | 1800319 |  |  | 0
Balance |  |  |  | 1800319 |  |  | 90000
Piedmont Plaster 16 Gypsum board |  |  |  | PO#
| 2990630 | [5 empty] | 3160630 | 170000
CO# | Amount | Pay Date | Pay # | Amount
1
2
Total | 2990630 |  |  | 0
Balance |  |  |  | 2990630 |  |  | 170000
James River Iron-17 - Misc. Metals |  |  |  | PO#
| 1814738 | [5 empty] | 1904738 | 90000
CO# | Amount | Pay Date | Pay # | Amount
1
2
Total | 1814738 |  |  | 0
Balance |  |  |  | 1814738 |  |  | 90000
STOVALL Engr. Bldg Prod.-18 - Metal Panels & Louvers |  |  |  | PO#
| 1448751 | [5 empty] | 1518751 | 70000
CO# | Amount | Pay Date | Pay # | Amount
1
2
Total | 1448751 |  |  | 0
Balance |  |  |  | 1448751 |  |  | 70000
eTEC Fire Protection -19 Fire Prot. Systems |  |  |  | PO#
| 587600 | [5 empty] | 616600 | 29000
CO# | Amount | Pay Date | Pay # | Amount
1
2
Total | 587600 |  |  | 0
Balance |  |  |  | 587600 |  |  | 29000
Augusta Steel Corp - 20 HM Doors, Frames & HDW |  |  |  | PO#
| 325506 | [5 empty] | 341506 | 16000
CO# | Amount | Pay Date | Pay # | Amount
1
2
Total | 325506 |  |  | 0
Balance |  |  |  | 325506 |  |  | 16000
TOTAL |  |  |  | 15463098.17 |  |  | 2941100.32 | 4674000
Balance | [7 empty] | 1732899.68
contractor payment log

## Close out
Updated 11/22/06
P.O. # | Package # | Contractor | CO Status | Punchlist | Closeout Docs. | CO13 | CO13.2 | Ret. | CLOSED
269543 | 207-16281-02 | Faulconer Construction (PG) |  |  |  | X | X | X | X
290227 | 207-16281-03 | Sumter Utilities |  |  |  | X | X | X | X
275954 | 207-16281-04 | Cleveland Cement (PG) |  |  |  | X | X | X | X
306970 | 207-16281-05 | Faulconer Construction (Arena) |  |  |  | X | X | X | X
317105 | 207-16281-06 | Shockey Precast Group |  |  |  | X | X | X | X
314843 | 207-16281-07 | Cleveland Cement (Arena) |  |  |  | X | X | X | X
321203 | 207-16281-08 | Hirschfeld Steel Corporation |  |  |  | X | X | X | X
348890 | 207-16281-09 | Shockey Precast Group |  |  |  | X | X | X | X
406947 | 207-16281-10 | ThyssenKrupp Elevator
378144 | 207-16281-11 | Bat Masonry |  |  |  | X | X | X
373407 | 207-16281-12 | Roof Services Corporation |  |  |  | X | X | X | X
343945 | 207-16281-13 | Colonial Mechanical | CO #43-48/UVA |  |  | X |  | 1.2%
333364 | 207-16281-14 | Design Electric Inc. | CO #98 w/UVA |  |  | X
349687 | 207-16281-15 | East Coast Glass Systems Inc. | CO #6,7,8 w/UVA |  |  |  |  | 0.2%
363670 | 207-16281-16 | Piedmont Plaster and Drywall, Inc. |  |  |  | X | X | X
354389 | 207-16281-17 | James River Iron
365843 | 207-16281-18 | W. H. Stovall and Company |  |  |  | X | X | X | X
369335 | 207-16281-19 | eTEC Fire Protection |  |  |  | X | X | X | X
368981 | 207-16281-20 | Augusta Steel Corporation |  |  |  | X | X | X
376973 | 207-16281-21 | Alexander Waterproofing Co., Inc |  |  |  | X | X | X | X
452498 | 207-16281-22 | K Plus |  |  |  | X | X | X
466762 | 207-16281-23 | G.C. Zarnas (Spray Fireproofing) |  |  |  | X | X | X | X
409769 | 207-16281-24 | Faulconer Construction Company (NGC) |  |  |  | X | X | X | X
467548 | 207-16281-25 | G.C. Zarnas (Painting) |  |  |  | X | X | X | X
467975 | 207-16281-26 | Creative Cabinets
455773 | 207-16281-27 | David Allen Company |  |  |  | X | X