## Procurement Issues
DETERMINATIONS AND FINDINGS FOR PROCUREMENT ISSUES
University of Virginia
Facilities Management
Facilities Planning and Construction
Prepared By: | Timothy Roland |  | TWR | Date: | 2007-06-28
Reviewed By: | George Southwell |  | GSS | Date: | 2007-06-28
Reviewed By: | Patricia Clifton |  | Patricia Clifton | Date: | 2007-06-28
Reviewed By: | Jeff Moore |  | Jeff Moore | Date: | 2007-06-28
Reviewed By: | Sack Johannesmeyer |  |  | Date:
Under emergency conditions, procure the furnishing and installation of new electrical controls and breakers in the University Hospital Generator Switchboard through a sole-source procurement with XYZ Company in accordance with FM Directive 320F.
GENERAL INFORMATION:
Project Title: |  | University Hospital Emergency Power Upgrade
Work Order Number: |  | 647753
Project Number: |  | P02047
Project Cost: |  | $1,452,220.00 (construction cost $700K)
Location: |  | University Hospital
Requestor: |  | Thomas A. Harkins
Project Manager: |  | Richard A. Fletcher
Funding Approved By: |  | Thomas A. Harkins
Completion Date: |  | January '08
BACKGROUND: (use ALT-ENTER for new paragraph. Use continuation page if necessary)
The emergency power for the University Hospital is provided by a distribution system that is nearing 20 years in age. As the hospital has expanded and new medical technologies have been incorporated, the emergency power requirements have expanded. The emergency power distribution system has not expanded. There remains sufficient generating capacity. However, the breakers at the Generator Switchboard are too small to fully utilize this capacity. (See Continuation)
DETERMINATION: (use ALT-ENTER for new paragraph. Use continuation page if necessary)
Given these facts, sufficient funding has been approved to design a complete upgrade in the Emergency Power System and implement the design in several phases. The first phase is replacing the existing 3,200 amp breakers with 5,000 amp breakers and upgrading the generator switchboard controls using current technology. The lead time for the 5,000 amp breakers and controllers is approximately 20-24 weeks. By selecting a contractor up-front and allowing them to proceed with the procurement of the breakers and controls, the equipment (See Continuation)
FINDING: (use ALT-ENTER for new paragraph. Use continuation page if necessary)
(Note: In this section state the dollars and/or time to be saved and/or reliability, quality or other improvement to be achieved by this action).
The current situation with the University Hospital's emergency power distribution system constitutes an emergency as defined in FM Directive No. 320F. Consequently, a contractor should be selected without competitive bidding as provided for in the directive. Given the past success with XYZ Company and based on their experience with the University Hospital's electrical infrastructure, they should be awarded this project.
| Approved: |  |  | Date:
Donald E. Sundgren
Copy: Project File, Procurement File, Maxine Maupin

## Continuation
DETERMINATIONS AND FINDINGS FOR PROCUREMENT ISSUES
CONTINUATION
BACKGROUND: (Continued) Also, the controls on the switchboard are dated. Currently, every request for a new connection to the emergency power system must be off-set by the removal of an equal load. The Hospital has reached the point where this is no longer an option. For example, the new Pharmacy Cleanroom is scheduled to come on line in the first quarter of 2008. Because of new mandated standards, the new emergency power load will be substatially higher than the load for the current Pharmacy facility. This project will not be allowed to come on line without an increase in the facility's emergency power distribution capacity.
DETERMINATION: (Continued) delivery will be allowed to run concurrently with the finalization and review of the construction documents. It would also eliminate the time required for RFP development and bidding. It is estimated that 3 months could be saved by this approach.
Emer. Procurement:
Order Breakers & Controls Jul '07
Complete Contract Documents Aug '07
Receive Breakers & Controls Dec '07
Installation Jan'08
Normal Procurement:
Complete Contract Documents Aug '07
Procure Electrical Contractor Oct '07
Order Breakers & Controls Oct '07
Receive Breakers & Controls Mar '08
Installation Apr '08
Given the criticality of expanding the Hospital's emergency power distribution capacity, any reasonable means of shortening the schedule is justified. The contractor under consideration for this project is XYZ Company. XYZ Company has a demonstrated ability to perform well on technically complex power projects. XYZ Company has provided emergency services to the Hospital on several instances in support of Health System Physical Plant. Additionally, XYZ Company completed all of the recent work on the main electrical infrastructure as a part of the Hospital Expansion Project. XYZ Company has a strong record of past performance in the University Hospital. Of all of the electrical contractors that have worked in the hospital, they have the most thorough knowledge of the hospital's emergency power system and its operation.