## Sheet1
Pkg | Group | RFP | UVA PC# | Description | Type of | Advertise | Receive | Evaluate | Advertise | Issue Bid | Pre-Bid | Bids Due | Open Bids | Interview | Notice to | PO#
# |  | 07- | 207-16528- |  | Bid | for Pre-Qual | for Pre-Qual | & Short List | for Bids | Package | Meeting | Date | Date | Date | Proceed
[6 empty] | Info. | Info. | Bidders
ISSUE YELLOW-OUTS (STRUCTURAL) 5/15/07
ASSUME ISSUE FINALS 6/14/07
1 | 1 |  | 002 | Early Site & Utilities | LS |  |  |  | 2/4/07(A) | 2/5/07(A) | 2/15/07(A) | 3/22/07(A) | 3/23/07(A) | N/A | 4/2/07 (A) | 600466
|  |  |  | CONTRACTOR PARTNERING MEETING | [6 empty] | 4/24/07(A)
2 | 2 | 105 | 004 | Structural Steel, Metal Deck, Metal Stairs | RFP | 3/18/07(A) | 4/17/07(A) | 4/30/07(A) | N/A | 5/21/07(A) | 5/31/07(A) | 7/10/07(A) | N/A | 6/29/07(A) | 9/21/07(A) | 665880
3 | 2 |  | 012 | Drilled Concrete Piers and Shafts | LS |  |  |  | 5/20/07(A) | 5/21/07(A) | 5/31/07(A) | 6/20/07(A) | 6/21/07(A) | N/A | 7/6/07(A) | 651544
4 | 2 |  | 013 | CIP Foundations, Concrete Slabs & Walls | LS |  |  |  | 5/20/07(A) | 5/21/07(A) | 5/31/07(A) | 7/10/07(A) | 7/11/07(A) | N/A | 10/4/07(A) | 654259
5 | 3 | 106 | 005 | Brick (Material Only) | RFP |  |  |  | 4/15/07(A) | 4/16/07(A) | 4/26/07(A) | 6/6/07(A) | N/A | N/A | 6/20/07(A)
6 | 3 | 108 | 006 | Architectural/Structural Precast Concrete | RFP | 4/29/07(A) | 5/30/07(A) | 6/7/07(A) | N/A | 6/18/07(A) | 6/27/07(A) | 7/25/07(A) | N/A | 7/30/07(A) | 9/21/07(A)
7 | 3 | 109 | 007 | Masonry (install) & Cast Stone | RFP | 4/29/07(A) | 5/31/07(A) | 6/7/07(A) | N/A | 6/18/07(A) | 6/27/07(A) | 8/7/07(A) | N/A | 8/13/07(A) | 9/25/07(A)
8 | 3 |  | 017 | Studs, drywall, Doors, frames & Hdw, rough carp., | LS |  |  |  | 6/17/07(A) | 6/18/07(A) | 6/27/07(A) | 8/8/07(A) | 8/9/07(A) | N/A | 10/3/07(A)
Insulation, Wood Windows
9 | 4 | 110 | 008 | Mechanical, Plumbing, Auto Temp. Control | RFP | 5/6/07(A) | 6/5/07(A) | 6/12/07(A) | N/A | 7/2/07(A) | 7/11/07(A) | 8/8/07(A) | N/A | 8/20/07(A) | 9/25/07(A)
10 | 4 | 111 | 009 | Electrical, Fire Alarm, Communications | RFP | 5/6/07(A) | 6/7/07(A) | 6/12/07(A) | N/A | 7/2/07(A) | 7/11/07(A) | 8/9/07(A) | N/A | 8/21/07(A) | 9/24/07(A) | 665508
11 | 4 |  | 019 | Fire Protection | LS |  |  |  | 7/15/07(A) | 7/16/07(A) | 7/26/07(A) | 8/15/07(A) | 8/16/07(A) | N/A | 9/24/07(A)
12 | 5 | 112 | 010 | Metal and EPDM Roofing and Panels | RFP | 5/13/07(A) | 6/12/07(A) | 7/20/07(A) | N/A | 7/25/07(A) | 8/2/07(A) | 8/28/07(A) | N/A | 9/13/07(A) | 10/29/07(A)
13 | 5 | 113 | 011 | Al. Clad Wood Windows and Doors | RFP | 5/13/07(A) | 6/13/07(A) | 7/20/07(A) | N/A | 7/24/07(A) | 8/2/07(A) | 8/30/07(A) | N/A | 9/6/07(A) | 2007-09-11
14 | 5 |  | 018 | Curtainwall, Louvers | LS |  |  |  | 7/15/07(A) | 7/16/07(A) | 7/26/07(A) | 8/22/07(A) | 8/23/07(A) | N/A | 9/21/07(A)
15 | 5 |  | 022 | Waterproofing & Green Roofs | LS |  |  |  | 8/5/07(A) | 8/6/07(A) | 8/16/07(A) | 9/11/07(A) | 9/12/07(A) | N/A | 10/2/07(A)
16 | 5 |  | 020 | Not Used
17 | 6 |  | 023 | Elevators [RE-BID] | LS |  |  |  | 2007-11-25 | 2007-11-27 | 2007-12-06 | 2008-01-03 | 2008-01-04 | N/A | 2008-01-25
18 | 6 |  | 024 | Spray Fireproofing | LS |  |  |  | 8/5/07(A) | 8/6/07(A) | 8/16/07(A) | 9/13/07(A) | 9/14/07(A) | N/A | 10/1/07(A)
19 | 6 |  | 026 | Metal Fabrications, Misc. Steel, Rails | LS |  |  |  | 8/12/07(A) | 8/13/07(A) | 8/23/07(A) | 9/27/07(A) | 9/28/07(A) | N/A | 9/21/07(A)
20 | 6 |  | 025 | Caulking, Expansion Control Joints | LS |  |  |  | 8/5/07(A) | 8/7/07(A) | 8/16/07(A) | 9/20/07(A) | 9/21/07(A) | N/A | 2007-10-02
21 | 7 |  |  | Not Used
22 | 7 |  | 028 | Acoustical Panel Ceilings | LS |  |  |  | 8/26/07(A) | 8/27/07(A) | 9/11/07(A) | 9/26/07(A) | 9/27/07(A) | N/A | 2007-10-12
23 | 7 | 117 | 015 | Domus Ceiling/Wood Ceilings (Metal with wood veneer) | RFP | 6/17/07(A) | 7/17/07(A) | 7/24/07(A) | N/A | 8/19/07(A) | 8/29/07(A) | 9/21/07(A) | N/A | 10/1/07(A) | 10/1/07(A)
24 | 7 |  | 027 | Painting & Wall coverings | LS |  |  |  | 8/26/07(A) | 8/27/07(A) | 9/11/07(A) | 10/11/07(A) | 10/12/07(A) | N/A | 2007-10-26
25 | 7 | 118 | 016 | Site Improvements - Concrete walks & Plaza, Paving, | RFP | 6/17/07(A) | 7/18/07(A) | 7/24/07(A) | N/A | 8/19/07(A) | 8/29/07(A) | 10/10/07(A) | N/A | 10/15/07(A) | 2007-10-30
|  |  |  | Fencing & Gates, Masonry Ret'g Walls, Bus Stop | [7 empty] | 90% OF COST BY LATE SEP.
26 | 8 |  |  | Fixed Audience Seating - BY UVA MATERIALS DEPT. | LS |  |  |  | N/A | 9/17/07(A) | N/A | 10/1/07(A) | 10/3/07(A) | 2007-10-16 | 2007-10-30
27 | 8 |  |  | Module Signage System PROCESS TBD | LS |  |  |  | 11/5/07(?)
28 | 8 | 121 | 021 | Resilient & vinyl flooring, base & carpet | RFP | 7/29/05(A) | 8/29/07(A) | 2007-09-26 | N/A | 10/1/07(A) | 10/16/07(A) | 11/6/07(A) | N/A | 11/21/07? | 12/5/07?
29 | 8 |  |  | Terrazzo Flooring | LS |  |  |  | 9/16/07(A) | 9/17/07(A) | 9/27/07(A) | 10/25/07(A) | 10/26/07(A) | N/A | 2007-11-02
30 | 9 |  | 030 | Millwork, P-Lam, wood base | LS |  |  |  | 10/21/07(A) | 10/22/07(A) | 11/6/07(A) | 2007-11-20 | 2007-11-21 | N/A | 2007-12-19
31 | 9 |  | 031 | Ceramic & stone tile | LS |  |  |  | 11/4/07(A) | 11/5/07(A) | 2007-11-15 | 2007-12-04 | 2007-12-05 | N/A | 2007-12-19
32 | 9 |  |  | Stone Benches and Specialties | RFP | TBD |  |  | N/A | 11/15/07(?)
33 | 9 |  | 032 | Landscaping | LS |  |  |  | 11/11/07(A) | 11/12/07(A) | 2007-11-28 | 2007-12-11 | 2007-12-12 | N/A | 2007-12-21
34 | 9 |  |  | Roller Shades | LS |  |  |  | 2007-11-18 | 2007-11-19 | 2007-11-28 | 2007-12-06 | 2007-12-07 | N/A | 2007-12-21
|  |  | Notes: | LS - Lump Sum/Low Bid
RFP - Technical & Cost Proposals
Pre-Bid Meetings combine multiple Bid Packages in the same meeting
(A) Actual Date
(*) All dates to be confirmed by UVA Procurement Department