## Sheet1
| CM TRADE PROCUREMENT TRACKING CHART (Last Update) | [12 empty] | Project Title
| ACTION >>> | Chair Appointment Letter |  |  | Shortlist Recommendation Letter |  |  | Recommendation Approval |  | Invitation Letters |  |  | RFP # | Award Recommendation Letter |  |  | Award Approval |  | Award/Reject Letters
| DIRECTION >>> |  | CFO to Chair |  |  | Chair to CFO |  | CFO to Chair |  |  | To Trades |  |  |  | Chair to CFO |  | CFO to Chair |  |  | To Trades
| PACKAGE DESCRIPTION | Drafted | Signed | Sent | Drafted | Signed | Sent | Signed | Sent | Drafted | Signed | Sent |  | Drafted | Signed | Sent | Signed | Sent | Drafted | Signed | Sent
#
1 | Early Site Utilities
2 | Structural Steel, Metal Deck, Metal Stairs
3 | Drilled Concrete Piers & Shafts
4 | CIP Foundations, Concrete Slabs & Walls
5 | Brick (Material Only)
6 | Architectural/Structural Precast Concrete
7 | Masonry (install) & Cast Stone
8 | Studs, Drywall, Doors, Frames & HDW, Rough Cap, Insulation
9 | Mechanical, Plumbing, Auto Temp. Control
10 | Electrical, Fire Alarm, Communications
11 | Fire Protection
12 | Metal & EPDM Roofing
13 | Wood Windows
14 | Alum. Entrances, Storefront, Curtain Walls, Glazing, Louvers, Exterior Shutters
15 | Membrane & Fluid Applied Waterproofing
16 | Not Used, Product moved to Storefront
17 | Elevators
18 | Spray Fireproofing
19 | Metal Fabricators, Misc. Steel, Rails
20 | Caulking
21 | Expansion Control Joints
22 | Acoustical Panel Ceilings
23 | Domus Ceiling/Wood Ceilings
24 | Painting & Wall Coverings
25 | Site Improvements – Concrete Walks & Plaza, Paving, Fencing & gates, Masonry Retaining Walls, Bus Stop
26 | Fixed Audience Seating
27 | Module Signage System
28 | Resilient & Vinyl Flooring, Base & Carpet
29 | Terrazzo Flooring
30 | Millwork, P-Lam, Wood Base
31 | Ceramic Stone Tile
32 | Stone Benches & Specialties
33 | Landscaping
34 | Roller Shades