## Procurement Issues
DETERMINATIONS AND FINDINGS FOR PROCUREMENT ISSUES
University of Virginia
Facilities Management
Facilities Planning and Construction
Prepared By: | Project Manager |  | Brian Pinkston | Date: | 2007-06-26
Reviewed By: | Division Manager |  | George S. Southwell | Date: | 2007-06-26
Reviewed By: | Patricia Clifton |  | Patricia Clifton | Date: | 2007-06-27
Reviewed By: | Jeff Moore |  | Jeff Moore | Date: | 2007-06-27
Reviewed By: | Sack Johannesmeyer |  |  | Date:
ACTION REQUESTED: (Use ALT-ENTER for new paragraph)
Per request from University ITC, allow emergency procurement of construction services from Moore's Electrical and Mechanical for installation of new cellular phone integration equipment in the Telephone Exchange Building.
GENERAL INFORMATION:
Project Title: |  | Telephone Exchange Bldg. Cellphone Integration Project
Work Order Number: |  | 693298
Project Number: |  | P02138
Project Cost: |  | 82132
Location: |  | Telephone Exchange Building
Requestor: |  | Jim Jokl (ITC)
Project Manager: |  | Brian Pinkston
Funding Approved By: |  | Jim Jokl (ITC)
Completion Date: |  | 2007-08-15
BACKGROUND: (use ALT-ENTER for new paragraph. Use continuation page if necessary)
The University has entered into a contract with Longent LLC to improve radio communication reception throughout Grounds, both within and outside buildings. The initial targets for improvement are the Alderman and McCormick Residence Hall complexes, the JPJ Arena and the football stadium. Improvements in both cellular telephone and public service radio reception in these areas are needed. [See CONTINUATION PAGE.]
DETERMINATION: (use ALT-ENTER for new paragraph. Use continuation page if necessary)
Since the intent of this project is to guarantee the safety of life and property, this project qualifies as an emergency project according to Directive 320F. Moore's Electrical and Mechanical was considered the ideal contractor because a) they can deliver the project on the correct schedule; b) they performed excellently on the Stacey Hall Generator project which was also an emergency project; and c) they are experienced in working in the West Complex.
FINDING: (use ALT-ENTER for new paragraph. Use continuation page if necessary)
(Note: In this section state the dollars and/or time to be saved and/or reliability, quality or other improvement to be achieved by this action).
Allow non-competitive award of this work to Moore's Electrical and Mechanical.
| Approved: |  |  | Date:
Donald E. Sundgren
Copy: Project File, Procurement File, Maxine Maupin

## Continuation
DETERMINATIONS AND FINDINGS FOR CODE/DESIGN ISSUES
CONTINUATION
Background Continued:
The urgency of this project has increased in importance due to the Virginia Tech shooting incident and the subsequent decision by UVa to put an emergency notification system in place by the time students return in the Fall. The emergency notification system will be capable of sending short text messages to staff and students' cell phones. This service was announced to UVa staff by Leonard Sandridge on 18 May and is being publicized to new students during their orientation. Therefore, it is imperative that the initial cellular phone reception improvements be available by Back to School Day on 25 August.
Longent has committed to making this date. To do so, UVa must provide space for new communications equipment that Longent will install. ITC will provide space for this equipment in the Telephone Exchange Building. A work order has been initiated that requires the installation of additional power and cooling capacity in the building. ITC requests that this project be given sufficient priority to insure the additional electrical capacity is in place by 23 July 2007 so the initial new communications equipment can be installed and tested. The HVAC addition should be completed by 15 August, recognizing the lead time required for equipment procurement. This will enable all Longent work for the initial target sites to be completed prior to Back to School Day